
For discussion

on 25 May 2010
Legislative Council Panel on Development
Progress Report on Kai Tak Development
Purpose


This paper updates Members on the progress of Kai Tak Development (KTD) and invites Members’ views on our further work, particularly a 2-stage pubic engagement exercise recently commenced in mid May 2010 for the preservation of Lung Tsun Stone Bridge.
OVERVIEW
2.
KTD is a highly complex development project spanning a total planning area of over 320 hectares covering the ex-Kai Tak airport together with the adjoining hinterland districts of Kowloon City, Wong Tai Sin and Kwun Tong.  The vision is to develop Kai Tak into “a Distinguished, Vibrant, Attractive and People-oriented area by the Victoria Harbour” with a mix of community, housing, business, tourism and infrastructural uses.
3. In January 2009, we briefed the Legislative Council (LegCo) Panel on Development (the Panel) on the KTD implementation plan which grouped various interrelated projects into three packages targeted for completion in 2013, 2016 and 2021.  These packages seek to ensure that the developments in Kai Tak will be taken forward in a coordinated and progressive manner, while taking into consideration their relative priorities and readiness to proceed.
4. In mid-2009, the Administration obtained funding approval from LegCo for proceeding with the design and/or construction of seven KTD-related public works projects with aggregate approved project estimates of about $3.7 billion.  Subsequently in November 2009 and April 2010, funding approval was also given respectively for the site formation works and the building works of the cruise terminal development with total approved project estimates of about $8.2 billion.
5. In November 2009, we updated the Panel on the progress of the KTD and obtained support for setting up a dedicated Kai Tak Office (KTO) in the Kowloon Development Office of the Civil Engineering and Development Department (CEDD) with a view to enhancing the delivery of KTD.  Following funding approval in February 2010 for creation of the supernumerary post of Head(KTO), the office started operation in March 2010.
PROGRESS
6. Key components of the first KTD package targeted for completion in 2013 are now under active construction, comprising the cruise terminal building cum first berth at the ex-runway, the public housing development at the north apron, and the associated supporting infrastructure.  In parallel, we are proceeding with the detailed planning and design of the subsequent KTD packages targeted for completion in 2016 and beyond.
(A) Projects for Completion in 2013
7. 

A plan showing the location of KTD projects currently under tender and construction stages for completion in 2013 is at Annex 1.  Whilst the building contract for the cruise terminal development has just been awarded earlier this month, the site formation works have been in smooth progress since commencement in late November 2009 with major activities currently focusing on piling works and dredging at seawall toe.  To tie in with the target commissioning of the first berth in mid-2013, construction of advance infrastructure works to provide access and utilities to the cruise terminal from Kowloon Bay is also in full swing.
8. 

At the north apron area, the public housing development for some 34 000 inhabitants commenced construction in June 2009 aiming at first population intake in early 2013.  Construction of the supporting infrastructure, including new roads and footbridges as well as enhancement of subways linking adjoining areas, is progressing simultaneously.

9. 

KTD will be served by the District Cooling System (DCS) which is a large-scale centralised air-conditioning system planned to serve the public and private non-domestic developments.  The project is now in the tender assessment stage.  CEDD maintains regular liaison with the Electrical and Mechanical Services Department on the interface issues to ensure timely completion of the first phase of DCS in 2013 to serve the cruise terminal and public housing developments.       
(B) Infrastructure Works under Planning/Design
10. In parallel, we are undertaking the detailed planning and design of infrastructure works under the other two KTD packages targeted for completion in 2016 and beyond, and are pursuing a number of issues requiring further public engagement/consultation as highlighted below.  
Lung Tsun Stone Bridge (the Bridge)
11. Remnants of the Bridge and the former Kowloon City Pier have been discovered in the north apron of Kai Tak.  Given its high historical significance, the remnants will be preserved in-situ as a special cultural heritage asset.  This conservation approach was endorsed by the Antiquities Advisory Board in December 2009.  A 2-stage public engagement (PE) exercise is being launched on conservation of the Bridge and its integration with KTD.  More information on the PE programme is at Annex 2.

12. The Bridge site deserves special treatment to signify its historical context and linkage to the Kowloon Walled City.  The site will become a feature of KTD with roots in the history of Hong Kong other than being just a former airport.  Through building consensus on the preservation options, a proper balance between conservation and development in Kai Tak is being explored.
Kai Tak River
13. The KTD planning sees transformation of the existing Kai Tak nullah at the north apron into a river channel as a key landscaped feature.  The river channel will form a major green corridor in shaping the public space in the city centre.  The river will traverse the commercial developments and make possible a pleasant riverside walk with shop frontage and eating places.  A conceptual scheme of the river, often quoted as Kai Tak River, is at Annex 3.
14. Whilst Drainage Services Department (DSD) is managing the nullah improvement works north of KTD, a coordinated approach will be necessary to rehabilitate/beautify the channel both upstream and downstream of Prince Edward Road East.  CEDD will collaborate with DSD to launch a PE exercise in late 2010 on the design of the entire river channel.
Enhanced Greening and quality urban design
15.
To realise the planning vision of creating a “Green Web for Sustainable Development”, we will seek to maximise the greening opportunities and achieve landscape works of a high quality in KTD.   The Kai Tak Office will draw up a coordinated framework covering various aspects of landscape design and urban design, such as greening ratio, building setback from lot boundaries, building separation, theme and character of individual areas within KTD, guidelines on landscape design, etc., for application to both public and private developments in KTD with a view to creating a high quality environment for business, living and leisure.  There will be an abundance of open space in KTD, which will be developed in an integrated manner with the objective of enhancing public accessibility and introducing vibrancy and variety to KTD. 

16.
As KTD has a long development programme up to around 2021, to ameliorate any adverse visual impact of ongoing construction activities on other projects already completed and on the neighbouring areas of KTD, mitigation measures, including interim greening, decorative hoarding and screen planting, will be adopted at appropriate locations so as to maintain a pleasant environment throughout the development period.

Accessibility to Waterfront
17.
In the design development of infrastructure works started in mid-2009, we are reviewing the practicality of fine-tuning the layout of KTD to enhance accessibility to the waterfront.  We are looking into possible improvement measures such as increasing the width of promenades, reducing the coverage of roads along the waterfront, and introducing greater vibrancy to these areas.  We are actively exploring an option to shift the roads along the ex-runway away from the waterfront (Annex 4) thereby releasing the waterfront areas for promenades for public enjoyment.  We will consult the public before firming up the proposals.
18.
We are also looking for early opportunities to open up other waterfront areas for public enjoyment.  In this connection, a 200-metre long section of the Kwun Tong Public Cargo Working Area was vacated and converted into the first stage of Kwun Tong Promenade in January 2010.
Integration with Adjacent Districts
19.
We are developing the design of planned pedestrian facilities (Annex 5) to further strengthen integration of KTD with existing urban fabrics.  In addition to new subways and footbridges, existing pedestrian links will be enhanced to symbolise their function as entrance to a new development area.  Themes reflecting the heritage of the locality will be considered for adoption in the design of these facilities as appropriate, such as aviation, street scene, etc.  Additional pedestrian links are also under consideration to strengthen the connectivity.
20.
In end 2009, we commenced a detailed feasibility study of the proposed Kai Tak Environmentally Friendly Transport System (EFTS).  Apart from examining the engineering, environmental, financial and operational issues, the study will also explore the scope of further enhancing inter-connection with the adjacent districts and facilitate their revitalization by extending the EFTS outside Kai Tak.  We have collected initial views from the District Councils on the EFTS study, the preliminary results of which will be available in late 2010 for further public consultation.
Mitigation of Odour
21.
Following the recommendations of the environmental impact assessment for KTD approved in March 2009, the design of in-situ bioremediation treatment to the sediments at Kai Tak Approach Channel and Kwun Tong Typhoon Shelter to mitigate odour is in progress.  The effectiveness of the treatment will be monitored upon completion of the works.  We will carry out in-depth analysis and consult the public before taking a decision on the proposed opening at the ex-runway.     
22.
On water quality in and adjacent Kai Tak, we commenced further monitoring works in December 2009 to establish a baseline for evaluating the effectiveness of the proposed improvement works.  The data obtained to-date indicate that the dissolved oxygen level is comparable with previous monitoring results.  To address the concern about the water quality at To Kwa Wan and Ma Tau Kok waterfront, we have formed an inter-departmental working group to work closely with the Kowloon City District Council.  Apart from stepping up regular maintenance of the drainage systems and enforcement actions against illegal discharges, we have constructed additional sewage interception facilities and arranged de-silting near the drainage outfalls.
Major Transport Infrastructure

23.
As for major transport infrastructure, the preliminary design of all Route 6 sections is in progress.  Route 6 planned through Kai Tak comprises three sections: the Central Kowloon Route (by Highways Department (HyD)), Trunk Road T2 and the Tseung Kwan O – Lam Tin Tunnel (both by CEDD).  With respect to the Shatin to Central Link, which is planned to run through the north apron area with two stations, HyD is consulting the public on the railway scheme whilst design work is on-going.

Communication with Public

24.
To further enhance our communication on KTD with the public, we will be issuing regular newsletters to report on the progress of this project.  The first edition of the newsletter will be published in mid-2010.
ADVICE SOUGHT

25.
Members are invited to note and provide comments on the latest progress of KTD.

Development Bureau

May 2010
1

