Section I	 	Standard Amendments to NEC TSC HK Edition

[Note to project office:

(i)	only the “Clause No.” and “Details” columns should be incorporated as part of the contract,

(ii)	the other columns are for project office’s reference only during tender/contract preparation and should not be incorporated as part of the contract, and

(ii)	the use of text in blue in “Details” column is for reference only, to highlight the differences from the original text. All text in “Details” column should be converted to black.]

I:1	Amendments to Core Clauses

| Clause No. | Applicable main Option(s) | Details | Rationale | Reference |
| --- | --- | --- | --- | --- |
| 11.2 | A & C | Replace the two references to “government” in sub-clause (3) with “Government”. | The term “Government” should be capitalised. | N.A. |
| 11.2 | A & C | Re-number the following sub-clauses: Option A NEC Clause 11.2(22), (25) & (27) to 11.2(27), (30) and (32); Option C NEC Clause 11.2(23), (24), (26) & (27) to 11.2(28), (29), (31) & (32); and Option E NEC Clause 11.2(23), (24), (26) & (28) to 11.2(28), (29), (31) & (33). | To align the numbering of the sub-clauses under NEC Clause 11.2 across various main Options. | N.A. |
| 11.2 | C | Replace the whole sub-clause (29) by the following: “Disallowed Cost is cost which • is not justified by the Contractor’s accounts and records, • should not have been paid to a Subcontractor or supplier in accordance with its contract, • was incurred only because the Contractor did not ─ follow an acceptance or procurement procedure stated in the contract, ─ give any early warning which the contract required it to give, ─ give notification to the Service Manager of the preparation for and conduct of an adjudication, a mediation, an arbitration or proceedings of a tribunal between the Contractor and a Subcontractor or supplier or ─ pay its Subcontractor or supplier in accordance with the subcontract in a timely manner, • was incurred due to a Subcontractor suspending or reducing the rate of progress of its work pursuant to the security of payment provisions, and the cost of •Plant and Materials not used to Provide the Service (after allowing for reasonable wastage) unless resulting from a change to the Scope, a Task or the Affected Property, •correcting Defects after Task Completion, •correcting Defects caused by the Contractor not complying with a constraint on how it is to Provide the Service stated in the Scope, • resources not used to Provide the Service (after allowing for reasonable availability and utilisation) or not taken away from the Service Areas when the Service Manager requested and • preparation for and conduct of an adjudication, a mediation, an arbitration or proceedings of a tribunal between the Parties.” | Add “, a mediation, an arbitration” after “give notification to the Service Manager of the preparation for and conduct of an adjudication” in the third sub-bullet point of the third main bullet point. Rationale To modify the definition of Disallowed Cost to suit the use of mediation or arbitration as options for settlement of disputes. | N.A. |
|  |  |  | Replace “or” at the end of the second sub-bullet point of the third main bullet point with a comma. Add “or” to the end of the third sub-bullet point of the third main bullet point. Add the following as a new fourth sub-bullet point of the third main bullet point: “• pay its Subcontractor or supplier in accordance with the subcontract in a timely manner,” Rationale To define Disallowed Cost which was incurred due to the Contractor not paying its Subcontractor or supplier in a timely manner. |  |
|  |  |  | Add the following as a new main fourth bullet point after the third main bullet point: “• was incurred due to a Subcontractor suspending or reducing the rate of progress of its work pursuant to the security of payment provisions”. As stated in Contract Data Part one, the security of payment provisions means the provisions contained in the Construction Industry Security of Payment Ordinance (Cap. 652). Rationale To define Disallowed Cost which was incurred due to a Subcontractor suspending or reducing the rate of progress of its work pursuant to Cap, 652. | DEVB Technical Circular (Works) (“TCW”) No. 6/2021 with update promulgated in DEVB’s memo dated 23.4.2025 |
| 11.2 | A | Replace the whole sub-clause (30) by the following: “The Price for Service Provided to Date is the total of: - for items stated in the Price List which the Contractor has completed, the Contract Rate multiplied by the quantities, - for items not stated in the Price List which the Contractor has completed, the prices assessed in the same way as a compensation event is assessed; and - notwithstanding the aforesaid, if the Contractor applies for the standard base value in accordance with NEC Clause 50.10 to 50.12 of the additional conditions of contract for an item, such item is excluded from the first and second bullet points above. Instead, the standard base value is added to the Price for Service Provided to Date. Completed work is work without notified Defects the correction of which will delay the work of the Contractor, the Client or Others. | To modify the definition of the Price for Service Provided to Date to suit NEC TSC contracts in Hong Kong. Third bullet is applicable if standard base value is adopted. This bullet should be adopted in conjunction with clause 11.2(32) & 50.10 to 50.12. |  |
| 11.2 | A & C | Replace the whole sub-clause (32) by the following: “The Prices are: - for items stated in the Price List, the Contract Rate multiplied by the quantities, - for items not stated in the Price List, the prices assessed in the same way as a compensation is assessed; and - notwithstanding the aforesaid, if the Contractor applies for the standard base value in accordance with NEC Clause 50.10 to 50.12 of the additional conditions of contract for an item, such item is excluded from the first and second bullet points above. Instead, the standard base value is added to the Prices.” | To modify the definition of the Price for Service Provided to Date to suit NEC TSC contracts in Hong Kong. Forth bullet is applicable if standard base value is adopted. This bullet should be adopted in conjunction with clause 11.2(30) & 50.10 to 50.12. |  |
| 11.2 | A & C | Add a new sub-clause (34) as follows: “The Contract Rate means the appropriate rate or lump sum stated in the Price List, multiplied by the relevant contract percentage and rounded off to the nearest cent.” | To add the definition of the Contract Rate to suit TSC contracts in Hong Kong. Contract Rate is a generic term that encompasses both rate and lump sum amount, depending on the context. |  |
| 11.2 | A & C | Add a new sub-clause (35) as follows: “Final Certificate is the certificate issued by the Service Manager upon the later of - the end of the Service Period - the end of the latest performance review period and - the last notified Defect which the Contractor has corrected in accordance with NEC Clause 43.4 or, as the case may be, which has been accepted by the Service Manager not to be corrected with an instruction given to change the Scope and the Prices in accordance with NEC Clause 44.1 and 44.2.” | To add the definition of the Final Certificate with respect to the whole TSC contract to suit the Hong Kong context. |  |
| 11.2 | A | Add a new sub-clause (36) as follows: “Imported Items are Plant and Materials imported from any place outside Hong Kong.” | To enable special payment for Imported Items. This amendment should be made in conjunction with clause 50.2B and 50.3. | SDEV’s memo ref. DEVB(W) 510/33/02 dated 8.7.2022 and 22.11.2023 |
| 12.6 to 12.11 | A & C | Add new sub-clauses 12.6 to 12.11 after sub-clause 12.5 as follows: 12.6 All references to “this contract” or “the contract” are to the contract as supplemented or amended from time to time. 12.7 All references to the “conditions of contract” are to the conditions of contract described in Part One of the Contract Data and as supplemented or amended from time to time. 12.8 All references to the “additional conditions of contract” are to the additional conditions of contract described in Part One of the Contract Data and as supplemented or amended from time to time. 12.9 All references to a condition, clause, sub-clause or provision of the conditions of contract or additional conditions of contract are to the condition, clause, sub-clause or provision of the conditions of contract or additional conditions of contract, and as supplemented or amended from time to time. 12.10 Headings are inserted for ease of reference only and shall not affect construction of the contract. 12.11 References in the contract to a document shall: - include all schedules, appendices, annexures and other materials attached to such document, and - mean the same as supplemented or amended from time to time.” |  |  |
| 14.1 | A & C | Add “, nor do the Service Manager’s assessments, certificates or other acts or omissions” at the end of the clause. | To widen the scope of activities of the Service Manager that are expressed not to change the Contractor’s responsibility for the works in order to retain the Contractor’s liability despite the administrators’ acts. | GCC 2(4), GCC 7(5), GCC 16(2), SCC73(2) |
| 16.1 | A & C | Add a new sub-clause 16.1A after sub-clause 16.1 as follows: “If the Contractor’s proposal contains or amounts to a Cost Savings Design as defined in ACC Clauses VII:1 and VII:2, this clause [*and NEC Clause 63.12] does not apply to such proposal and the Contractor complies with the relevant requirements set out in the additional conditions of contract including but not limited to ACC Clause VII:3.” [*insert NEC Clause 63.12 for Option A] | To clearly delink the Cost Savings Design as set out under ACC VII:1 and VII:2 from the Contractor’s proposals under this clause 16. |  |
| 19.6 | A & C | Replace the second sentence by the following: “Where items of works in the Task price list are covered by Contract Rate, the items are priced using the Contract Rate.” | To suite TSC contracts in Hong Kong |  |
| 22.1 | A & C [Optional] | Replace the whole clause 22.1 by the following new clause 22.1 “Subject to ACC Clause II:2(3), the Contractor provides the team structure and staff including key persons as identified in the Tender Submissions or necessarily inferred therefrom.” | This is only used when tenders are evaluated using a marking scheme, i.e. ACC II:2 is adopted. The project office should list out the key persons in the Contract Data Part two for the Contractor to input where appropriate. |  |
| 22.3 | A & C [Optional] | Add a new clause 22.3 as follows: “If any key person is not identified in the Contract Data, the Contractor submits the name, relevant qualifications and experience of each key person to the Service Manager for acceptance within [two weeks] of the Contract Date.” | This is only used when tenders are evaluated using a formula, i.e. ACC II:2 is NOT adopted. The project office should list out the key persons in the Contract Data Part two for the Contractor to input where appropriate. The project office should update the time in square bracket to suit their projects. | SDEV’s memo ref. DEVB(W) 510/17/01 dated 16.7.2010 SCC68 SCC 68A |
| 24.2 | C | Replace the whole clause 24.2 by the following new clause 24.2: “The Contractor submits the name of each proposed Subcontractor with the relevant information on the proposed subcontract to the Service Manager for acceptance. A reason for not accepting the Subcontractor is that - its appointment will not allow the Contractor to Provide the Service, - the proposed prices or rates for the subcontract submitted by the proposed Subcontractor are not competitive or at open market prices or rates, or its proposed terms for the subcontract contain activities or items which are substantially over or under-priced, or erratically priced, or - its appointment/selection does not comply with any provision relating to sub-contracting in the contract. The Contractor does not appoint a proposed Subcontractor until the Service Manager has accepted it.” | To take into account ICAC's concern on the potential erratic pricing issue in subcontracts. | N.A. |
| 24.3 | A & C | Replace “.” At the end of the second bullet with “or”; Add the following new bullet point after the second bullet point as follows: “they do not require a Subcontractor to comply with the relevant subcontracting requirements set out in the contract.” | To supplement potential reasons of withholding an acceptance to the Contractor’s proposed conditions of subcontracts. | N.A. |
| 27 | A & C | Delete the whole clause 27 | Relevant provision is set out in ACC Clause II:3. | N.A. |
| 30.3 | A & C | Add the following sentences at the end of after the first sentence: “The Service Manager decides the date of Task Completion and certifies it within three weeks of the date or, if a different period is stated in the Contract Data, within the period stated.” | To introduce a Completion certificate for each Task Order. | N.A. |
| 50.2A | A | Add a new clause 50.2A after clause 50.2 as follows: “The Contractor may in an application for payment referred to in clause 50.2 apply for payment of Plant and Materials which - are not individually itemised in the Price List, - have not been included in any completed work, and - are not prematurely delivered to and not improperly stored on the Site (“Relevant Plant and Materials”). The Contractor shall clearly identify in the application for payment the amount claimed and the item in the Price List to which the Relevant Plant and Materials will be included (“Relevant Item”), and submit to the Service Manager all relevant supporting documents. If on the assessment date to which the application for payment relate, the Service Manager is satisfied that the Relevant Plant and Materials - are not individually itemised in the Price List, - have not been included in any completed work, and - are not prematurely delivered to and not improperly stored on the Site, the Serivce Manager may assess the amount due to the Contractor for such Relevant Plant and Materials by reference to rates and lump sums of the Relevant Item (“Advance Payment for Plant and Materials”).” | To enable payment for materials on site. This amendment should be made in conjunction with clause 50.3. | GCC Cl. 79(1)(c) |
| 50.2B | A | Add a new clause 50.2B after clause 50.2A as follows: “The Contractor may in an application for payment referred to in clause 50.2 apply for payment of an Imported Item which is - purchased or imported into Hong Kong ahead of time due to supply shortages or logistics disruptions, - properly and securely stored at a premises in Hong Kong (“Premises”) but is not yet due to be delivered by the Contractor to the Site, and - clearly demarcated from any other materials at the Premises. (“Relevant Imported Item”) The Contractor shall clearly identify in the application for payment of the Relevant Imported Item the amount claimed and the item in the Price List to which the Relevant Imported Item relate (“Related Item”) and submit to the Service Manager all relevant supporting documents, including but not limited to evidence of purchase or importation of the Relevant Imported Item, evidence of supply shortage or logistic disruptions, the original date agreed by the Service Manager for delivery of the Relevant Imported Item to the Site (if applicable), the address of the Premises, and photographs showing the condition of the Relevant Imported Item and the manner in which it is stored. If on the assessment date to which the application for payment relate, the Service Manager is satisfied that the Relevant Imported Item is - purchased or imported into Hong Kong ahead of time due to supply shortages or logistics disruptions, - properly and securely stored at the Premises but is not yet due to be delivered by the Contractor to the Site, and - clearly demarcated from any other materials at the Premises, the Service Manager shall assess the amount due to the Contractor for such Relevant Imported Item by reference to the rates and lump sums of the Related Item (“Special Payment”).” | To enable special payment for Imported Items. This amendment should be made in conjunction with clause 11.2(30), 50.2A and 50.3. | SDEV’s memo ref. DEVB(W) 510/33/02 dated 8.7.2022 and 22.11.2023 |
| 50.3 | A | Replace the whole clause 50.3 by the following new clause 50.3: “If the Contractor submits an application for payment two weeks before the assessment date, the amount due at the assessment date is the amount calculated in the manner below based on the Service Manager’s assessment for each of the following items: • the Price for Service Provided to Date, • plus Advance Payment for Plant and Materials, • plus Special Payment, • plus other amounts to be paid to the Contractor, • in respect of any item included in the assessment of the Price for Service Provided to Date, less Advance Payment for Plant and Materials and Special Payment already made in respect of that item, if any, • less amounts to be paid by, retained from or deducted from the Contractor. The actual amount due shall be certified by the Service Manager and paid in accordance with clause 51.” | Add the 2nd, 3rd and 5th bullet points as appropriate if Advance Payment for Plant and Materials and / or Special Payment is executed in accordance with 50.2A and 50.2B respectively. Rationale To enable payment for materials on site and / or special payment for Imported Items. This amendment should be made in conjunction with clause 11.2, 50.2A and 50.2B as appropriate. | GCC Cl. 79(1)(c) |
| 50.3 | C | Add a fourth bullet point as follows: “• less the Service Manager’s interim assessment of the Contractor’s share deduction as at the share assessment date.” | To cater for payment deduction, if any, before arriving at the amount due, and avoid overpayment by specifying the Service Manager’s right to deduct the Contractor’s pain share assessed during the contract period. This should be read in conjunction with clauses 53.1 to 53.4. Also to standardise the calculation on payment deduction. | N.A. |
| 50.10 to 50.12 | A [Optional] | Add new sub-clauses 50.10 to 50.12 as follows: 50.10 The Contractor may apply for the standard base value as the amount due to it for Task Completion of a Task Order. 50.11 If the Service Manager issues an instruction changing the Scope after the Contractor’s application, the Contractor confirms within one week of the Service Manager’s instruction whether it still intends to apply for the standard base value for such Task Order. If the Contractor does not confirm its intention within one week of the Service Manager’s instruction, it is regarded that the Contractor does not intend to apply for the standard base value for such Task Order. 50.12 The standard base value is not subject to any deduction or addition as provided in the contract except that it is subject to the following: - price adjustment for inflation under NEC Clause X1, - deduction under NEC Clause 82.4, and/or - additional interest payment under NEC Clause 51. | Applicable if standard base value is adopted. This amendment should be made in conjunction with clause 11.2(30) & (32). |  |
| 51.3 | A & C | Delete the first and second bullet point. | To omit the Client’s liability to pay interest if the Service Manager corrects in a later certificate due to compensation events or other reasons. | GCC 79(4) |
| 54.2A | C | Add a new clause 54.2A after clause 54.2 as follows: “The Service Manager makes interim assessments of the Contractor’s share on each share assessment date using its forecast of the final Price for Service Provided to Date and its forecast of the final total of the Prices. The Service Manager informs the Contractor of its interim assessment of the Contractor’s share deduction.” | To specify the Service Manager’s right to make interim assessment of the Contractor’s share and the Service Manager’s obligation to inform the Contractor of its assessment. This clause should be read in conjunction with clause 50.2. Also to standardise the calculation on payment deduction. | N.A. |
| 60.1 | A & C | Add a new bullet point to the end of clause 60.1(1) as follow: “a change to a Task or any part thereof which is within part of the service.” | To avoid unnecessary administrative burden in managing extra CE | N.A. |
| 60.1 | A & C [Optional] It should be used when tenders are evaluated using a marking scheme. | Replace the second bullet of sub-clause (1) by the following new bullet: “a change to the Tender Submissions which is made” | The coverage of Tender Submissions is wider than “Scope provided by the Contactor for its design”. | ETWB TC(W) No. 8/2004 Appendix C and SDEV’s memo ref. DEVB(W)546/84/01 of 30.10.2009 |
| 61.4 | A & C | Replace the first bullet point by the following: “three weeks after the Contractor’s notification or, if confirmation of no objection is required from the Client, six weeks after the Contractor’s notification or” | To impose specific time limit for the Service Manager to notify its decision on compensation events to the Contractor. Approval should be sought from the relevant authorities in accordance with the Stores and Procurement Regulations (SPR) 520 and Appendix V(B) and the consultancy agreement terms where appropriate. | N.A. |
| 61.4 | A & C | Replace the 2nd and 3rd sentences by the following: “If the event - arises from a fault of the Contractor, - has not happened and is not expected to happen, - has not been notified within the timescales set out in these conditions of contract, - has no effect upon Defined Cost or a Task Completion, - is an instruction given by the Service Manager which has effect upon Defined Cost or a Task Completion or an instruction given by the Service Manager to stop or not start any work, provided that these instructions are necessary for the safety and health of any person or the safety of any property on or adjacent to the Service Areas and such necessity does not arise from: - a fault of the Client or any person employed by or contracted to it, except the Contractor, - a fault in the design contained in the Scope provided by the Client, - a fault in the design contained in an instruction from the Service Manager changing the Scope, - war, civil war, rebellion, revolution, insurrection, military or usurped power, - strikes, riots and civil commotion not confined to the Contractor’s employees, - radioactive contamination, or - is not one of the compensation events stated in the contract, the Service Manager notifies the Contractor that the Prices and Task Completion Date are not to be changed and states the reasons in the notification. Otherwise, the Service Manager notifies the Contractor that the event is a compensation event and includes in the notification an instruction to the Contractor to submit quotations.” | To avoid any ambiguities in interpretation of the contract provisions in respect of the safety and health of any person or the safety of any property on or adjacent to the Service Areas. | SDEV’s memo ref. DEVB(W) 546/83/01 dated 9.5.2024 |
| 61.7 | A & C | Replace clause 61.7 by the following new clause 61.7: “A compensation event is not notified by the Service Manager or the Contractor later than eight weeks after the issuance of the Final Certificate.” | To suit TSC contacts in Hong Kong | N.A. |
| 62.2 | A & C unless comments/ endorsement have been sought for the deviation from this standard amendment from the Inter- departmental Working Group and/or the Steering Committee. | Replace clause 62.2 by the following new clause 62.2: “Quotation for a compensation event comprise proposed changes to the Prices and any delay to a Task Completion Date assessed by the Contractor. If a compensation event is stated in clause 63.6, its quotations exclude proposed changes to the Prices. The Contractor submits details of the assessment with each quotation. If the programme for remaining work is altered by the compensation event, the Contractor includes the alterations to the Accepted Plan or the Task Order Programme in the quotation.” | To impose specific conditions where the Contractor is only entitled for extension of time due to certain compensation events. This amendment should be made in conjunction with clause 62.2 and 63.6. | N.A. |
| 62.3 | A & C | Replace the second sentence of clause 62.3 by the following: “The Service Manger replies within three weeks of the submission or, if confirmation of no objection is required from the Client, six weeks of the submission.” | To impose specific time limit for the Service Manager to reply to the Contractor for its quotation for compensation events. Approval should be sought from the relevant authorities in accordance with the Stores and Procurement Regulations (SPR) 520 and Appendix V(B) and the consultancy agreement terms where appropriate. | N.A. |
| 63.1 | A & C | Replace clause 63.1 by the following new clause 63.1: “For a compensation event which only affects the quantities of work shown in the Price List, the change to the Prices is assessed by multiplying the changed quantities of work by the appropriate Contract Rate as determined by the Service Manager.” | To suit TSC contracts in Hong Kong. | N.A. |
| 63.2 | A [Optional] The project office shall seek approval from a public officer of D2 rank or above for use of this amendment and document the justifications. | Replace “For other compensation events,” in the first sentence by the following: “For other compensation events, subject to the provisions of clause 63.3,” | To follow the generic NEC principle in assessing compensation events based on Defined Cost plus the resulting Fee basis, this amendment should be avoided as far as practicable. Only if the specific contract requires, this amendment is made in conjunction with clause 63.3 to impose specific conditions that compensation events are primarily based on Contract Rate. | N.A. |
| 63.3 | A [Optional] The project office shall seek approval from a public officer of D2 rank or above for use of this amendment and document the justifications. | Replace the whole clause 63.3 by the following new clause 63.3: “Where the effect of a compensation event is changes to the Prices, the assessment of the compensation event will be based on the Contract Rate, instead of the Defined Cost and the resulting Fee, under the scenarios specified in sub-clauses (i) to (iii) below: (i) Any item omitted is assessed at the Contract Rate except that in the absence of the Contract Rate, the assessment of the item omitted is at a rate or lump sum based on Defined Cost and the resulting Fee. (ii) Any work carried out which is the same as or similar in character to and executed under the same or similar conditions and circumstances to any item priced in the Price List is assessed at the Contract Rate for such item. (iii) Any work carried out which is not the same as or similar in character to or is not executed under the same or similar conditions or circumstances to any item priced in the Price List is assessed at a rate or lump sum based on the Contract Rate so far as may be reasonable, failing which, at a rate or lump sum based on Defined Cost and the resulting Fee. For the avoidance of doubt, any assessment based on the Contract Rate is not subject to adjustment of the fee percentage.” | To follow the generic NEC principle in assessing compensation events based on Defined Cost plus the resulting Fee basis, this amendment should be avoided as far as practicable. Only if the specific contract requires, this amendment is made in conjunction with clause 63.2 to impose specific conditions that compensation events are primarily based on Contract Rate. | N.A. |
| 63.7 | A unless comments/endorsement has been sought for the deviation from this standard amendment from the Inter- departmental Working Group and/or the Steering Committee. | Replace clause 63.7 by the following new clause 63.7: “The rights of the Client and the Contractor to changes to the Prices and the Task Completion Dates are their only rights in respect of a compensation event. Notwithstanding the foregoing, for compensation events under clauses 60.1(6), 60.1(21), 60.1(22) or 60.1(23), the Contractor has no rights to changes to the Prices. Nor will the assessment of changes to the Prices for other compensation events be affected by any concurrent compensation event under clauses 60.1(6), 60.1(21), 60.1(22) or 60.1(23).” | To impose specific conditions where the Contractor is only entitled for extension of time due to certain compensation events. This amendment should be made in conjunction with clause 62.2 and 63.7. | N.A. |
| 63.7 | C unless comments/endorsement has been sought for the deviation from this standard amendment from the Inter- departmental Working Group and/or the Steering Committee. | Replace clause 63.7 by the following new clause 63.7: “The rights of the Client and the Contractor to changes to the Prices and the Task Completion Dates are their only rights in respect of a compensation event. Notwithstanding the foregoing, for compensation events under clauses 60.1(6), 60.1(21)(fourth and fifth bullet points), 60.1(22) or 60.1(23), the Contractor has no rights to changes to the Prices. Nor will the assessment of changes to the Prices for other compensation events be affected by any concurrent compensation event under clauses 60.1(6), 60.1(21)(fourth and fifth bullet points), 60.1(22) or 60.1(23).” | To impose specific conditions where the Contractor is only entitled for extension of time due to certain compensation events. This amendment should be made in conjunction with clause 62.2 and 63.7. The project office may add any of the items under sub-clause 60.1(21) after reviewing their project specific situations and such proposal or other amendments shall be approved by DEVB. | N.A. |
| 70.1 | A & C | Add “in order to Provide the Service” after “within the Service Areas” in the first sentence. | To clarify, only the Plant and Materials brought to the Service Area for the purpose of providing the service are included, not all Plant and Materials present in the Service Areas. |  |
| 83.4 | A & C | Add a new clause 83.4 as follows: “If the Contractor cannot provide an insurance required by the contract in the form specified in the Scope, the Contractor submits proposal for changes to the form for providing insurance as close as practically possible to the form to the Service Manager for acceptance. The Contractor includes in the proposal a quotation for reduced Prices as a result of the changes. A reason for not accepting the proposal is that the insurance does not provide cover for the events stated in the insurance table. The Service Manager - notifies the Contractor of its acceptance of the proposal and quotation or - if it does not agree with the Contractor’s quotation, notifies the Contractor of an assessment of the reduced Prices made by it. The Service Manager changes the Scope and the Prices accordingly.” | To impose specific requirements for procurement of construction related insurance according to ETWB TCW No. 7/2005. The project office should include the relevant form in the Scope. | ETWB TCW No. 7/2005 SCC 11 SCC 12 |
| 90.2 | A & C | Replace “R1–R15, R18 or R21” by “R1–R15, R18, R21, R22 or R23” in the first row of the Termination Table. | R5A is added to extend the circumstances to cover presentation of winding-up petition. | Email from DEVB dated 30.10.2025 |
| 90.3 | A & C | Replace “R1 to R15, R18 or R21” by “R1 to R15, R18, R21, R22 or R23” in the first line of second paragraph in this clause. |  |  |
| 91.1 | A & C | Add a new sub-bullet point before the first sub-bullet point of the second main bullet point as follows: “ – presented a petition for winding-up itself or had a petition for winding-up presented against it by any creditor (R5A),” |  |  |
| 91.8 | A & C | Add a new clause 91.8 after clause 91.7 as follows: “The Client may terminate if the Contractor has engaged or is engaging in acts or activities that are likely to constitute or cause the occurrence of offences endangering national security or which would otherwise be contrary to the interest of national security, or the continued engagement of the Contractor or the continued performance of the contract is contrary to the interest of national security (R22).” | R22 and 91.8 are added to align with Stores and Procurement Regulations (SPR) requirements on safeguarding national security interests. Amendment to 90.2, 90.3 and 91.8 should be made together. | As per SPR on national security interests. SDEV’s memo ref. DEVB(W) 510/30/01 dated 31.8.2022 |
| 91.9 | A & C | Add a new clause 91.9 after clause 91.8 as follows: “The Client may terminate if the Contractor is a joint venture and any participant or shareholder thereof does any act in ACC Clause IV:3(6) (R23).” | R23 and 91.9 are added to incorporate the reasons to terminate if any participant or shareholder in the joint venture encounters the specific financial situations as provided in ACC IV:3(6). | Email from DEVB dated 30.10.2025 |
| 92.2 | A & C | Replace the references to “P1”, “P2” and “P3 by “P2”, “P3” and “P4” respectively. | To correct the typo errors |  |
| 93.1 | A & C | Replace clause 93.1 by the following new clause 93.1: “The amount due on termination includes (A1) - an amount due assessed as for normal payments, - the Defined Cost for Plant and Materials which have been delivered and retained by the Client, - other Defined Cost reasonably incurred in expectation of completing the whole of the service, - any amounts retained by the Client and - a deduction of any un-repaid balance of an advanced payment.” | To align with ECC(HK) |  |

I:2	Amendments to Secondary Option Clauses

| Clause No. | Applicable main Option(s) | Details | Rationale | Reference |
| --- | --- | --- | --- | --- |
| X1.1 | A, C if contract price fluctuation is applicable. | Replace the whole clause X1.1 by the following: “X1.1 (1) The Base Date Index (B) is the latest available index figure applicable to the base date. (2) The Latest Index (L) is the latest available index figure applicable to the date 42 days before the date of assessment of an amount due. (Option 1) (2) The Latest Index (L) is the latest available index figure applicable to the date 42 days before the Task starting date of each Task Order. (Option 2) (3) The Price Adjustment Factor (PAF) at each date of assessment of an amount due is the total of the products of each of the proportions stated in the schedule of proportions multiplied by (L-B)/B for the index figure linked to it.” | To match with the price fluctuation mechanism promulgated through DEVB TC(W) No. 4/2021 and associated guidelines. "index figure " should be well defined in the Contract Data Part two. The Project Office should decide the applicable X1.1(2) option as appropriate. | DEVB TC(W) No. 4/2021 |
| X1.3 | A if contract price fluctuation is applicable. | Replace the whole clause X1.3 by the following: “X1.3 Each amount due includes an amount for price adjustment which is the sum of - the change in the Price for Service Provided to Date since the last assessment of the amount due multiplied by the PAF and; - the amount for price adjustment included in the previous amount due.;” | To match with the price fluctuation mechanism promulgated through DEVB TC(W) No. 4/2021 and associated guidelines. "index figure " should be well defined in the Contract Data Part two. | DEVB TC(W) No. 4/2021 |
| X1.4 | C if contract price fluctuation is applicable. | Replace the whole clause X1.4 by the following: “X1.4 Each time the amount due is assessed, an amount for price adjustment is added to the Prices which is the change in the Price for Service Provided to Date since the last assessment of the amount due multiplied by (PAF/(1+PAF))” | To match with the price fluctuation mechanism promulgated through DEVB TC(W) No. 4/2021 and associated guidelines. “index figure” should be well defined in the Contract Data Part two. | DEVB TC(W) No. 4/2021 |
| X1.5 | A & C | Replace the whole clause X1.5 by the following: “X1.5 The Defined Cost for compensation events is assessed using - the Defined Cost at base date levels for amounts calculated from the Contract Rate and - the Defined Cost current at the dividing date used in assessing the compensation event, adjusted to base date by dividing by one plus the PAF for the last assessment of the amount due before that dividing date, for other amounts.” | To match with the price fluctuation mechanism promulgated through DEVB TC(W) No. 4/2021. | DEVB TC(W) No. 4/2021 |
| X11 | A & C | Replace the whole clause X11 by the following: “X11.1 The Client may terminate the Contractor’s obligation to Provide the Service for a reason not identified in the Termination Table by notifying the Service Manager and the Contractor. X11.2 Without prejudice to the generality of clause X11.1, if the Service Manager certifies to the Client that in its opinion the completion of the service will be delayed by a period of not less than one year due to interfacing problems or programme slippages of associated works and services outside the scope of the contract, the Client may terminate the Contractor’s obligation to Provide the Service for convenience and thereafter Provide the Service itself or arrange for another contractor to Provide the Service. X11.3 If the Client terminates for a reason not identified in the Termination Table (including without limitation the reason stated in clause X11.2), the termination procedures followed are P1 and P2 and the amounts due on termination are A1 and A2. Payment to the Contractor under clause 53.1 shall be in full and final settlement of all claims, costs and charges incurred by the Contractor as a result of the contract. X11.4 The Contractor includes provisions equivalent to this clause in its subcontracts and supply contracts to reserve its power to terminate such subcontract or supply contract in the event of the termination by the Client under this clause. The Contractor is not entitled to compensation for any expenditure, liability and/or loss resulting from non-compliance with this requirement.” | To effect the right of the Government to terminate for convenience under ETWB TC(W) No. 23/2004. X11 and this amendment are to be included in all contracts. | ETWB TC(W) No. 23/2004 SCC 59 |
| X14.1 | A &C | Replace the whole sub-clause (1) by the following: “The Contractor may apply for an advance payment for a Task in an Advance Payment Statement if: - the Task Order for the Task is issued within the period stated in Contract Data, - the total of the Prices for the Task is more than the minimum amount and - the Task Completion Date is not within the minimum period after the Task starting date.” |  |  |
| X14.3 | A &C | Replace the first sentence by the following: “If the Contractor applies for an advanced payment for a Task, the Contractor submits an Advanced Payment Statement to the Service Manager with the quotation for a Task.” |  |  |

I:3	Amendments to Schedule of Cost Components

| Item No. | Applicable main Option(s) | Details | Rationale | Reference |
| --- | --- | --- | --- | --- |
| 13 | C | Replace the whole item (h) by the following: “protective clothing and site uniform” | To promote clarity on the cost component item. | N.A. |
| 41 | C | Replace the whole item 41 by the following: “Payments to Subcontractors accepted by the Service Manager for work which is subcontracted without taking into account any amounts paid to or retained from the Subcontractor by the Contractor, which would result in the Client paying, retaining or deducting the amount twice.” | To promote clarity on the cost component item where the Subcontractor being paid must have been accepted by the Service Manager. To avoid double deduction from the Contractor’s account. In the situation where the Contractor makes direct payment to a lower-tier subcontractor (as a claimant) for an unpaid adjudicated amount and then deducts such sum from any payment owed to his Subcontractor (first tier) under a Relevant Subcontract, such deduction in payment made to his Subcontractor (first tier) under that Relevant Subcontract should not be taken into account in the “Payments to Subcontractors for work which is subcontracted”. | N.A. DEVB TCW No. 6/2021 |