| Clause | Remarks/Guidelines |
| --- | --- |
| NTT B2 Constraints on *Project Manager*’spower | |
| 1. The tenderer’s attention is drawn to the constraints on the *Project Manager’s* powers set out in Clause [B1]# of the *additional conditions of contract*. | Please refer to WBTC Nos. 19/2000, 20/2000 and 16/2002, ETWB TCW Nos. 56/2002A and 6/2004, and DEVB TCW No. 5/2007  # Insert appropriate reference |
| (2) In addition to the above constraints, the *Project Manager* is also required under the terms of its appointment by the *Client* to: |
| (i) refer the details of every change to the Scope, including the reasons for the change and its estimated change to the Prices due to the associated compensation event, to the *Client* for information as soon as the change is ordered; |  |
| (ii) refer the details of the evaluation to the *Client* for information as soon as the change to the Prices due to the compensation event associated with the change to the Scope has been determined; |  |
| (iii) report to the *Client* all compensation events involving changes to the Prices and refer to the principles underlying its assessment of each compensation event to enable the *Client* to provide its view of the matter before the *Project Manager* reaches a decision; and |  |
| (iv) report to the *Client* all compensation events involving delays to the Completion Date and Key Dates and, except for those delays solely in respect of inclement weather conditions, refer to the principles underlying its assessment of each compensation event to enable the *Client* to provide its view of the matter before the *Project Manager* reaches a decision. |  |
|  | Please add any other constraints as necessary and specified in the consultancy agreements other than the above. |