GOVERNMENT OF HONG KONG

______________

GENERAL CONDITIONS OF CONTRACT

FOR

TERM CONTRACTS

FOR

BUILDING WORKS

CONTRACT NO.	OF 19    .

1988 EDITION

GF 545

Page

Table of Contents 		3

General Conditions of Contract		7

TABLE OF CONTENTS

Clause		Page

DEFINITIONS AND INTERPRETATION

1	(1)	Definitions	            7

(2)	Singular and plural 	            8

(3)	Marginal notes 	            8

(4)	Payment 	            8

(5)	Contract governed by Laws of Hong Kong 	            8

MAINTENANCE SURVEYOR AND MAINTENANCE

SURVEYOR'S REPRESENTATIVE

2	Duties and powers of the Maintenance Surveyor and the Maintenance Surveyor’s Representative 	            8

ASSIGNMENT AND SUB-LETTING

3	Assignment 	            9

4	Sub-letting	            9

CONTRACT DOCUMENTS

5	Documents mutually explanatory 	            9

6	Provision of Drawings and Schedule of Rates 	            9

7	Drawings provided by the Contractor for the Works 	          10

8	Information not to be divulged 	          10

9	Use of English language 	          10

GENERAL OBLIGATIONS

10	Extent of Contract 	          10

11	Contractor to execute Articles of Agreement 	          10

12	Sureties or security 	          11

13	Inspection of the Contract Area 	          11

14	Sufficiency of Tender 	          11

15	Works to be to the satisfaction of the Maintenance Surveyor 	          11

16	Order of executing the Works 	          11

17	Particulars to be furnished	          11

18	Contractor's superintendence 	          11

19	Contractor’s employees 	          12

20	Emergency Staff generally 	          12

21	Setting-out  	          12

22	Safety and security of the Works 	          12

23	Care of the Works 	          13

24	Damage to persons and property 	          13

25	Design responsibility 	          14

Clause	                                                                                                                                                                           Page

26	Interference with traffic and adjoining properties	          14

27	Remedy on failure to insure 	          14

28	Accident or injury to workmen	          14

29	Contractor to give notice of injury 	          14

30	Patent rights and royalties	          15

31	Giving of notices and payment of fees	          15

32	Compliance with enactments and regulations	          15

33	Notices to be written in English and Chinese	          15

34	Site diary and labour returns	          15

35	Fossils	          15

36	Facilities for other contractors	          16

37	Clearance of the Site on completion	          16

38	Publication of photographs of the Site or the Works	          16

39	Offering gratuities	          16

LABOUR

40	Site cleanliness 	          16

41	Engagement of labour 	          16

42	Fair wages 	          16

43	Passes 	          17

MATERIALS AND WORKMANSHIP

44	Quality of  materials and workmanship and tests 	          17

45	Access to the Site and places of manufacture 	          17

46	Examination of work before covering up 	          17

47	Uncovering and making openings 	          18

48	Removal of unsatisfactory material and work 	          18

COMMENCEMENT, COMPLETION AND DELAYS

49	Commencement of the Works 	          18

50	Occupation of the Site 	          18

51	Time for completion 	          19

52	Continuous or overtime working	          19

53	Extension of time for completion 	          19

54	Rate of progress 	          20

55	Liquidated damages for delay 	          20

56 	Completion of the Works	          20

SUSPENSION OF THE WORKS

57	Suspension of the Works 	          22

58	Suspension lasting more than 90 days 	          22

Clause	                                                                                                                                                                           Page

MAINTENANCE AND DEFECTS

59	Execution of work of repair 	          22

60	Temporary reinstatement 	          22

61	Investigating defects 	          23

62	Measurement of Works 	          23

63	Order for Variations	          23

64	Valuing variations	          24

65	Daywork	          24

66	Disturbance to the progress of the Works	          24

67	Notice of claims	          25

NOMINATED SUBCONTRACTORS

68	The Employer’s right to order work or materials from Specialist 	          25

69	Varied form of sub-contract and objections to nomination 	          26

70	Payment to Nominated Subcontractors 	          26

71	Assignment of Nominated Sub-contractor’s obligations  	          27

CONSTRUCTIONAL PLANT, TEMPORARY BUILDINGS AND MATERIALS

72	Vesting of Constructional Plant and temporary buildings 	          27

73	Vesting of materials 	          27

74	Removal of Constructional Plant, temporary buildings and materials 	          27

75	Hired and hire-purchase Constructional Plant 	          27

76	Employer's expense in entering into hire or hire-purchase agreement 	          28

77	Liability for loss or damage to Constructional Plant 	          28

78	Incorporation of certain Clauses in sub-contracts 	          28

CERTIFICATES AND PAYMENTS

79A	Submissions for payment for the Works 	          28

79B	Submissions for payment for the Works 	          28

80A	Interim payments 	          29

80B	Interim payments	          29

81	Submission of statement of claims for interim payments	          30

82	Payment on certification	          30

83	Correction and withholding of certificates	          30

84	Interim payment certificate or certified bill not to constitute approval of work	          30

85	Approval works	          30

86	Maintenance Certificate	          30

REMEDIES AND POWERS

87	Forfeiture 	          31

88	Work by person other than the Contractor 	          32

89	Recovery of money due to the Employer 	          32

Clause	                                                                                                                                                                           Page

SPECIAL RISKS AND FRUSTRATION

90	Special risks 	          32

91	Frustration 	          33

SETTLEMENT OF DISPUTES

92	Settlement of disputes 	          33

NOTICES

93	Service of notices 	          34

DEFAULT OF THE EMPLOYER

94	Default of the Employer 	          35

GENERAL CONDITIONS OF CONTRACT

DEFINITIONS AND INTERPRETATION

Definitions

1.	(1)	 In the Contract the following words and expressions shall have the meaning hereby assigned to them except when the context otherwise requires:-

"Certificate of Completion” shall mean an appropriate certification by the Maintenance Surveyor or his representative on the Works Order.

"Complaint Chit” means a Works Order with an estimated value not exceeding the amount stated in the Appendix to the Form of Tender and is in all respects, other than for payment, referred to as a Works Order.

"Completion of a Works Order” shall mean the completion of all that part of the Works included in one Works Order.

“Completion of the Works” shall mean the completion of all Works Orders issued under the Contract.

"Constructional Plant” means all appliances or things of whatsoever nature required for the execution of the Works but does not include materials or other things intended to form or forming part of the permanent work or vehicles engaged in transporting any personnel, Constructional Plant, materials or other things to or from the Site,

"Contract” means the Articles of Agreement, the Tender and the acceptance thereof by the Employer, Drawings, General Conditions of Contract, Special Conditions of Contract if any, Specification and Schedule of Rates.

"Contractor“ means the person, firm or company whose Tender has been accepted by the Employer and includes the Contractor’s personal representative, successors and permitted assigns.

"Contract Area” means the area referred to in the Contract.

"Cost” means expenditure reasonably incurred including overheads whether on or off the Site and depreciation in value of  Constructional Plant owned by the Contractor but excluding profit.

"Drawings” means the Drawings referred to in the Specification or Schedule of Rates and any modification of such drawings approved in writing by the Maintenance Surveyor and such other drawings as may from time to time be furnished or approved in writing by the Maintenance Surveyor.

"Emergency Work” means such  work as is so classified by the Maintenance Surveyor.

"Employer” means the Government of Hong Kong.

"General Holiday” means every Sunday and other day which is a general holiday by virtue of the Holidays Ordinance.

"Maintenance Period” means the maintenance period named in the Appendix to the Form of Tender calculated from the date of completion of any Works Order or part thereof certified by the Maintenance Surveyor in accordance with Clause 56.

"Maintenance Surveyor” means the person named in the articles of Agreement as the Maintenance Surveyor or such other person as may be appointed from time to time by the Employer and notified in writing to the contractor to act as the Maintenance Surveyor for the purposes of the Contract.

"Maintenance Surveyor’s Representative” means any person or persons appointed from time to time by the Maintenance Surveyor and notified in writing to the Contractor to perform the duties set forth in Clause 2(2).

"Nominated Sub-contractor” means and includes all specialists, merchants, tradesmen and the like executing any part of the Works or supplying ant materials or services for the Works who shall have been or shall be nominated by the Employer and employed by the Contractor.

"Nominated  Working Hours” shall be deemed to be the period from 8.00 a.m. until 5.00 p.m.

"Portion” means a part of the Site separately identified in any Works Order.

"Schedule of Rates’ means the Schedule of Rates referred to in the Contract.

"Section “ means a part of the Works for which a separate time for commencement and/ or completion is identified in any Works Order.

"Site” means the lands and other places to which the Contractor is allowed access and limited occupation by the Employer for the purpose of the execution of the Works.

"Specification Contractor” means any contractor employed by the Employer to execute Specialist Works.

"Specialist Works” means any work separately identified in the Contract or in any Works Order and connected with or ancillary to the Works which may from time to time be carried out on the Site by a Specialist Contractor.

"Specification” means the specifications referred to in the Contract and any modification or addition as may be included in any Works Order or as may other or as may otherwise from time to time be furnished or approved in writing by the Maintenance Surveyor.

"Temporary Works” means all temporary work of every kind required for the construction, completion and maintenance of the Works.

“Works: means the work or services including work or services to be carried out by Nominated Sub-contractor to be constructed, completed, maintained and/or supplied in accordance with the Contract and includes Temporary Works, Emergency Works Ordered from time to time and detailed in a Works Order.

| “Works Order” means a written order signed by the Maintenance Surveyor and served to the Contractor or posted to the Contractor’s usual place of business for part of the Works or things to be executed, supplied or done by the Contractor under the Contract and includes but is not limited to a written Works Order in confirmation of a verbal Works Order or Complaints Chit. |
| --- |
| Singular and plural | (2) Words importing the singular only also include the plural and vice versa where the context requires. |
| Marginal notes | (3) The index and marginal notes or headings in the General Conditions of Contract, Special Conditions of Contract if any, and the Specification shall not be deemed to be part thereof or be taken into consideration in the interpretation or construction thereof. |
| Payment |

(4)	Unless otherwise provided, all payments shall be made in Hong Kong dollars.

| Contract governed by Laws of Hong Kong | (5) The Contract shall be governed by and construed according to the laws for the time being in force in Hong Kong. |
| --- | --- |
|  | MAINTENANCE SURVEYOR AND MAINTENANCE |
|  | SURVEYOR’S REPRESENTATIVE |
| Duties and powers of the Maintenance Surveyor and the Maintenance Surveyor's Representative |

2.	(1)	The Maintenance Surveyor shall carry out such duties as are specified in the Contract with due expedition.  Subject to the provisions of sub-clause (3) of this Clause the Contractor shall take instructions only from the Maintenance Surveyor.

(2)	The duties of the Maintenance Surveyor's Representative are to watch and inspect the Works, to test and examine any material to be used and workmanship employed by the Contractor in connection with the Works and to carry out such duties and exercise such powers vested in the Maintenance Surveyor as may be delegated to him by the Maintenance Surveyor in accordance with the provisions of sub-clause (3) of this Clause.

(3)	The Maintenance Surveyor may from time to time delegate to the Maintenance Surveyor’s Representative any of the duties and powers vested in him.  Any such delegation shall be in writing signed by the Maintenance Surveyor and shall specify the duties and powers thereby delegated.  No such delegation shall have effect until a copy thereof has been delivered to the Contractor.  Any written instruction or written approval given by the Maintenance Surveyor’s Representative to the Contractor within the terms of such delegation, but not otherwise, shall bind the Contractor and the Employer as though it had been given by the Maintenance Surveyor.

Provided that:-

(a)	failure of the Maintenance Surveyor’s Representative to disapprove any work or material shall not prejudice the power of the Maintenance Surveyor thereafter to disapprove such work or material;

(b)	if the Contractor or the Employer shall be dissatisfied by reason of any decision of the Maintenance Surveyor's Representative they may refer the matter to the Maintenance Surveyor who shall confirm, reverse or vary such decision.

(4)	No act or omission by the Maintenance surveyor or the Maintenance Surveyor’s Representative in the performance of any of his duties or the exercise of any of his powers under the Contract shall in any way operated to relieve the Contractor of any of the duties, responsibilities, obligations or liabilities imposed upon him by any of the provisions of the Contract.

| ASSIGNMENT AND SUB-LETTING |
| --- |
| Assignment | 3. The Contractor shall not assign the Contract or any interest therein without the written consent of the Employer and any assignment shall be in a form approved by the Employer. |
| Sub-letting |

4. 	(1)	The Contractor shall not sub-let the whole of the Works.  The contractor shall be permitted unless expressly prohibited by the Contract to sub-let a part of the Works either on the basis of the provision by the sub-contractor of labour and materials or by the provision of labour on a piece-work basis.

(2)	The Contractor shall be permitted to sub-let a part of the Works on the basis of provision of Constructional Plant by the sub-contractor, provided that such sub-letting is not expressly prohibited by the Maintenance Surveyor in writing within a period of 14 days from receipt by the Maintenance Surveyor of a request in writing from the Contractor.

(3)	Notwithstanding that the Maintenance Surveyor has not prohibited sub-letting under sub-clause (2) of this Clause the Maintenance Surveyor shall, if in his opinion he considers it necessary, have full power to instruct the removal of any sub-contractor from the Site and/or the Works which power shall not be exercised unreasonably.

(4)	The sub-letting of any part of the Works shall not relieve the Contractor from any liability or obligation under the Contract particularly in respect of the provision of superintendence in accordance with Clause 18 and he shall be responsible for the acts, defaults and neglects of any sub-contractor or the agents, employees or workmen of any sub-contractor as fully as if they were the acts, defaults or neglects of the Contractor, his agents, employees or workmen.

(5)	It shall be the duty of the Contractor if so required by the Maintenance Surveyor to furnish the Maintenance Surveyor with full particulars of any sub-contractor employed or to be employed on the Works.

CONTRACT DOCUMENTS

Documents mutually explanatory

5. 	(1)	Save to the extent that any Special Condition of Contract provides to the contrary the provisions of these General Conditions of Contract shall prevail over those of any other documents forming part of the Contract.

(2)	Subject to the foregoing the several documents forming the Contract are to be taken as mutually explanatory of one another but in case of ambiguities or discrepancies the same shall be explained by the Maintenance Surveyor  who shall issue to the Contractor instructions clarifying such ambiguities or discrepancies.  Where the Contractor makes a request in writing to the Maintenance Surveyor for instructions under this sub-clause the Maintenance Surveyor shall respond within 14 days of receipt of such request.

Provided that:-

(a)	work shown on the Drawings or described in the Specification but not referred to in the Schedule of Rates shall be dealt with in accordance with Clause 64;

(b)	if in the opinion of the Maintenance Surveyor compliance with such instructions shall involve the Contractor in any expense which by reason of any ambiguity or discrepancy the Contractor did not and had no reason to anticipate, the Maintenance Surveyor shall value such expense in accordance with Clause 64 and certify for payment accordingly;

(c) if in the opinion of the Maintenance Surveyor compliance with such instruction shall involve the Contractor in any saving then the Maintenance Surveyor shall value such saving and deduct the same form any payment due to the Contractor.

Provision of Drawings and Schedule of Rates

6. 	(1)	Two copies of the Drawings shall be furnished to the Contractor free of charge together with two copies of the Schedule of  Rates and Specification if requested by the Contractor.

(2)	The Maintenance Surveyor shall within 14 days of receiving a request in writing from the Contractor provide the Contractor with any further copies of the Drawings requested by the Contractor upon payment at the standard rate laid down form time to time by the Employer.

(3)	The Maintenance Surveyor shall issue to the Contractor from time to time during the progress of the Works such other Drawings and Specification as in the opinion of the Maintenance Surveyor may be necessary for the purpose of the execution of Works and the Contractor shall be bound by the same.

(4)	The Contractor shall give adequate notice in writing to the Maintenance Surveyor of other Drawings or Specification that may be required for the execution of the Works.

(5)	One copy of the Drawings furnished to the Contractor as aforesaid shall be kept by the Contractor at his office and the same shall at all reasonable times be available for inspection and use by the Maintenance Surveyor and the Maintenance Surveyor’s Representative and by any other person authorized by the Maintenance Surveyor in writing.

(6)	At the completion of the final Works Order the Contractor, if required by the Maintenance Surveyor, shall return to the Maintenance Surveyor all drawings and other Contract documents provided under the Contract, other than the Contractor’s signed copy of such Drawings or documents.

(7) All work executed under the Contract shall be measured in accordance with the instructions detailed in the Schedule of Rates and paid for at the rates printed therein and where applicable as amended by the percentage additions or omissions quoted by the Contractor in the Tender.

Drawings provided by the Contractor for the Works

7.	(1)	When the Contractor is required to provide Drawings or other documents in connection with the Works, unless the Contract provides to the contrary, all such Drawings and documents shall be submitted in duplicate to the Maintenance Surveyor at a reasonable time before the work shown or described thereon is to be carried out so as to permit the Maintenance Surveyor sufficient time to examine the Contractor’s proposals properly.  The Maintenance Surveyor shall give or refuse his approval in writing to such proposals within a reasonable time.

(2)	If the Maintenance Surveyor is not satisfied with the proposals set out in the Contractor’s Drawings or documents the Maintenance Surveyor may consider necessary.  The Contractor shall make and be bound by such amendments at no additional expense to the Employer.

(3)	The Contractor shall provide the Maintenance Surveyor with the type and number of copies of such Drawings and documents as may be specified in the Contract within 14 days of the Maintenance Surveyor’s  approval.

(4)	Should it be found at any time after approval has been given by the Maintenance Surveyor that the said Drawings or documents do not comply with the terms and conditions of the Contract or that the details do not agree with the Drawings or documents previously submitted and approved by the Maintenance Surveyor. the Contractor shall make such alterations or additions as in the opinion of the Maintenance Surveyor are necessary to remedy any non-compliance at the Contractor’s own expense.

(5) No examination by the Maintenance Surveyor of the Drawings or documents submitted by the Contractor under the provisions of this Clause nor any approval given by the Maintenance Surveyor of the same, with or without amendment, shall absolve the Contractor from any liability for the same.

Information not to be divulged

8.	(1)	The Contractor shall not use or divulge, except for the purpose of the Contract, any information provided by the Employer or the Maintenance Surveyor in the Contract documents or in any subsequent correspondence and documentation.

(2) The Employer and the Maintenance Surveyor may use any information provided by the Contractor in accordance with the Contract but shall not divulge such information except for the purpose of the Contract or for the purpose of carrying out any repair, amendment, extension or other work connected with the Works.

Use of English Language

9.	The Contract documents, all correspondence in connection with the Contract and Drawings or other documents provided by the Contractor in accordance with Clause 7 shall be in English.

|  | GENERAL OBLIGATIONS |
| --- | --- |
| Extent of Contract | 10. The Contractor shall, subject to the provisions of the Contract, execute the Works and provide all labour, materials, Constructional Plant, Temporary Works, transport to or from the Site or in or about the Works and everything whether of a temporary or permanent nature required in and for such execution so far as the necessity for providing the same is specified in or reasonably to be inferred from the Contract, The right is reserved by the Employer, at the discretion of the Employer to have any part of the Works carried out by means of a contract with others or by the use of the Employer’s work force and resources. |
| Contractor to execute Articles of Agreement |

11.	The Contractor when called upon to do so, shall enter into and execute Articles of Agreement which will be prepared at the expense of the Employer in the form provided by the Employer.

Sureties or security

12. The Contractor shall either: -

(a)	at his own expense obtain the guarantee in the form provided by the Employer of an insurance company or bank, in either case to be approved in writing by the Employer, to be jointly and severally bound together with him to the Employer in the sum provided in the Form of Tender for the due performance of the Contract, or

(b)	deposit with the Director of Accounting Services, Hong Kong Government, as security for the due performance of the Contract the sum provided in the Form of Tender.

Provided that when the maintenance certificate in respect of the Works is issued as provided in Clause 86 hereof the said guarantee or deposited sum shall be released or repaid to the Contractor.

Inspection of the Contract Area

13.	(1)	The Contractor shall be deemed to have examined and inspected the Contract Area and to have satisfied himself, before submitting his Tender, as regards existing roads or other means of communication with and access to the Site, the nature of the ground and sub-soil, the form and nature of the site, the risk of injury or damage to property, the nature of materials (whether natural or otherwise ) to be excavated, the nature of the work and materials necessary for the execution of the Works, the accommodation he may require and generally to have obtained his own information on all matters affecting his Tender and the execution of the Works.

| (2) No claim by the Contractor for additional payment shall be allowed on the ground of any misunderstanding in respect of the matters referred to in sub-clause (1) of this Clause or otherwise or on the ground of any allegation or fact that incorrect or insufficient information was given to him by any person whether in the employ of the Employer or not or of the failure of the Contractor to obtain correct and sufficient information, nor shall the Contractor be relieved from any risk or obligation imposed on or undertaken by him under the Contract on any such ground or on the ground that he did not or could not foresee any matter which may in fact affect or have affected the execution of the Works. |
| --- |
| Sufficiency of Tender | 14. The Contractor shall be deemed to have satisfied himself before submitting his Tender as to the correctness and sufficiency of his Tender for the Works and of the rates stated therein, which rates shall except in so far as it is otherwise provided in the Contract, cover all his risks, liabilities and obligations set out or implied in the Contract and all matters and things necessary for the proper execution of the Works. |
| Works to be to the satisfaction of the Maintenance Surveyor | 15. Save in so far as it is legally or physically impossible the Contractor shall execute the Works in strict accordance with the Contract to the satisfaction of the Maintenance Surveyor and shall comply with and adhere strictly to the Maintenance Surveyor’s instruction on any matter related to the Contract whether mentioned in the Contract or not. |
| Order of executing the Works | 16. The Contractor shall, if directed by the Maintenance Surveyor execute any part of a Works Order in such order and at such times and commencing from such points as may be required by the Maintenance Surveyor. In the absence of such directions the contractor may execute the work in such order and commencing at such point as is convenient to himself. The Maintenance Surveyor may at any time after the issuing of a Works Order change the previously required order of works, specify the order of works or order changes to points of ingress and egress to any work. |
| Particulars to be furnished | 17. The Contractor shall whenever required by the Maintenance Surveyor furnish for the Maintenance Surveyor’s information particulars in writing of the Contractor’s arrangements for carrying out any Works and of the Constructional Plant and Temporary Works which the Contractor intends to supply, use or construct as the case may be. The submission to and approval be the Maintenance Surveyor of such particulars shall not relieve the Contractor of any of his liabilities and obligations under the Contract. |
| Contractor's superintendence |

18.	(1)	The Contractor shall give or provide all necessary superintendence during the execution of the Works and as the Maintenance Surveyor may consider necessary for the proper fulfilment of the Contractor’s obligations under the Contract.

(2)	The Contractor shall ensure that he is represented by a competent and authorized English-speaking agent who shall be deemed to be approved by the Maintenance Surveyor provided such agent is not expressly disapproved by the Maintenance Surveyor in writing within 14 days from the serving of a notice in writing upon the Maintenance Surveyor by the Contractor of the appointment of such agent.  Such agent shall give his whole time to the superintendence of the Works.

(3)	The Maintenance Surveyor shall have the authority to withdraw his approval of the authorized agent at any time.  If such approval shall be withdrawn the Contractor shall, after receiving notice in writing of such withdrawal, remove the agent forthwith and shall not thereafter employ him again on the Works in any capacity and shall replace him by another competent English-speaking agent approved by the Maintenance Surveyor.

(4)	Such authorized agent shall receive on behalf of the Contractor directions and instructions from the Maintenance Surveyor and from the Maintenance Surveyor’s Representative.

(5) The Contractor shall ensure that there is available at all times a competent English -speaking person who will be responsible for dealing with all enquiries and requests made by the Maintenance Surveyor under the Contract and ensuring that these are immediately passed to the Contractor for implementation.

Contractor’s employees

19.	(1)	The contractor, and any of his sub-contractors, shall provided and employ on the Site in connection with the execution of the Works:-

(a)	only such technical personnel as are skilled and experienced in their respective trades and callings and such sub-agents, foremen and leading hands as are competent to give proper supervision to the work they are required to supervise, and

(b)	such skilled, semi-skilled and unskilled labour as is necessary for the proper and timely execution of the Works.

(2)	The Maintenance Surveyor shall be at liberty to object to and require the Contractor to remove forthwith from the Works any person employed by the Contractor or by a sub-contractor in or about the execution of the Works who in the opinion of the Maintenance Surveyor misconducts himself or is incompetent or negligent in the proper performance of his duties or whose employment is otherwise considered by the Maintenance Surveyor to be undesirable and such person shall not be again employed upon the Works without the written permission of the Maintenance Surveyor.

(3) Any person so removed from the Works shall be replaced as soon as possible by a competent substitute.

Emergency Staff generally

20.	The Contractor shall have available at all times workmen and plant for the execution of Emergency Work, and such workmen and plant shall be available without extra charge to the Employer except for any additional payment as detailed in the Contract.

Setting-out

21.	(1)	The Contractor shall be responsible for the true and proper setting-out of the Works in relation to original points, lines and levels of reference shown on any Drawing or schedule provided by the Maintenance Surveyor and for the correctness of the position, level, dimensions and alignment of all parts of the Works and for the provision of all necessary instrument, appliances and labour in connection therewith.

(2)	If at any time during the progress of the Works any error shall appear or arise in the position, level, dimensions or alignment of any part of the Works, the Contractor on being instructed so to do by the Maintenance Surveyor shall, at his own expense, rectify such error unless such error is based on incorrect data shown on any Drawing or document supplied to Contractor by the Maintenance Surveyor in which case the rectification shall be treated as a Variation in accordance with Clause 63.

(3) The checking of any setting-out or of any line or level by the Maintenance Surveyor shall not in any way relieve the Contractor of his responsibility for the correctness thereof and the Contractor shall carefully protect and preserve all bench-marks, site-rails, pegs and other things used in setting out the Works.

Safety and security of the Works

22.	(1)	The Contractor shall throughout the progress of the Works take full responsibility for the adequate stability and safety of all operations on the Site other than those of Specialist Contractors and utility undertakers and have full regard for the safety of all persons on the Site.  The Contractor shall keep the Site and the Works in an orderly state appropriate to the avoidance of danger to all persons.

(2)	The Contractor shall in connection with the Works provide and maintain all lights, guards, fences and warning signs and provide watchmen when and where necessary or required by the Maintenance Surveyor or by any competent statutory or other authority for the protection of the Works or for the safety and convenience of the public or others.

(3)	Where any work would otherwise be carried out in darkness, the Contractor shall ensure that all parts of the Site where such work is being carried out are so lighted as to ensure the safety of all persons on or in the vicinity of the Site and of such work.

(4) The Contractor, after obtaining any necessary approval from any relevant authority, shall submit to the Maintenance Surveyor proposals showing the layout of pedestrian routes, lighting. guarding and signing for any road opening or traffic diversion which may be required in connection with the execution of the Works. No such road opening or traffic diversion shall be brought into operation or used unless the proposals submitted have been previously approved by the Maintenance Surveyor and properly provided and implemented on the Site.

Care of the Works

23.	(1)	From and including the date for commencement of the Works notified by the Maintenance Surveyor in accordance with Clause 49 or from the date of occupation whichever is the earlier until 28 days after the date of completion of the Works certified by the Maintenance Surveyor in accordance with Clause 56 or until the date the Employer takes over the Works, if earlier, the Contractor shall take full responsibility for the care of the Works and subject to Clause 22(1) any Specialist Works or any part thereof, any Constructional Plant, temporary buildings and materials and things whatsoever on the Site or delivered to or placed on the Site in connection with or for the purpose of the Works or any Specialist Works.

Provided that if the Maintenance Surveyor shall issue a certificate of completion in respect of any Section before he shall issue a certificate of completion in respect of the whole of the Works the Contractor shall cease to be responsible for the care of that Section 28 days after the date of completion certified by the Maintenance Surveyor in respect of that Section and the responsibility for the care thereof shall thereupon pass to the Employer.

Provided further that the Contractor shall take full responsibility for the care of any outstanding work which he shall have undertaken to finish during the Maintenance Period until such outstanding work is complete, and shall continue to be responsible for all things which are required to be retained on the Site during the Maintenance Period including Constructional Plant, materials and temporary buildings and other facilities provided for the use of the Maintenance Surveyor, the Maintenance Surveyor’s Representative and their staff.

(2)	In case any damage, loss or injury from any cause whatsoever, except the excepted risks as defined in sub-clause (4) of this Clause, shall happen to the Works or any Specialist Works or any part thereof, or any Constructional Plant, temporary buildings, materials and things whatsoever on the Site, the contractor shall at his own expense and with all possible speed make good or at the option of the Employer shall pay to the Employer the cost of making good any such damage, loss or injury to the satisfaction of the Maintenance Surveyor and shall, notwithstanding such damage, loss or injury, proceed with the execution of the Works in all respects in accordance with the Contract and the Maintenance Surveyor’s instructions.

(3)	To the extent that any damage, loss or injury arises from any of the excepted risks defined in sub-clause (4) of this Clause, the Contractor shall if instructed by the Maintenance Surveyor repair and make good the same at the expense or proportionate expense of the Employer.  Any sum payable under this Clause by the Employer shall be determined by the Maintenance Surveyor in the same manner as a sum payable in respect of a variation ordered in accordance with Clause 63.

(4)	The ‘excepted risks’ are:-

(a)	outbreak of war (whether war be declared or not) in which Hong Kong shall be actively engaged;

(b)	invasion of Hong Kong;

(c)	act of foreign terrorists in Hong Kong;

(d)	civil war, rebellion, revolution or military or usurped power in Hong Kong;

(e)	riot, commotion or disorder in Hong Kong otherwise than amongst the employees of the Contractor, any sub-contractor or Specialist Contractor currently or formerly engaged on the Works or Specialist Works;

(f)	a cause due to the occupation by the Employer, his agents, employees, tenants or other contractors not being employed by the Contractor, of any part of the Works for a purpose other than the carrying out of Specialist Works;

(g)	damage, loss or injury which is the direct consequence of the Maintenance Surveyor’s design of the Works;

(h) a cause due to neglect or default by the Maintenance Surveyor or the Employer or their employees and agents in the course of their employment.

Damage to persons and property

24.	(1)	The Contractor shall, except if and so far as the Contract otherwise provides, indemnify and keep indemnified the Employer against all losses and claims for injury or damage to any person or property whatsoever, other than surface or other damage to land or crops on the Site, which may arise out of or in consequence of the execution of the Works or in the carrying out of the Contract and any losses or claims arising from the acts or omissions of the Contractors servants, agents, sub-contractors and employees and against all claims , demands, proceedings, damages, costs, charges and expenses whatsoever in respect thereof or in relation thereto.

(2)	The Contractor shall make good or at the option of the Employer shall pay to the employer the cost of making good any damage, loss or injury which may occur to any property of the Employer or any loss the Employer may suffer and shall recompense the Employer in respect of any damages, loss or injury which may occur to any employee of the employer by or arising out of or in consequence of the execution of the Works or in the carrying out of the Contract.

Provided that:-

(a)	the Contractor’s liability to indemnify or recompense the Employer under sub-clauses (1) and (2) of this Clause shall be reduced proportionately to the extent that the act or neglect of the Maintenance Surveyor or the Employer, their respective agents or employees shall have contributed to the damage, loss or injury;

(b)	nothing herein contained shall be deemed to render the Contractor liable for or in respect of or to indemnify the Employer against any compensation or damages for or with respect to:-

(i)	the use or limited occupation of land provided by the Employer for the Works, or for the purpose of executing the Works, or interference, whether temporary or permanent, with any right of way, light, air or water or other easement or quasi easement of the Works in accordance with the Contract, or

(ii)	the right of the Employer to construct the Works on, over, under, in or through any land,

or for, or in respect of all claims, demands, proceedings, damages, costs, charges and expenses thereof in relation thereto.

| (3) The indemnities given herein by the Contractor shall not be defected or reduced by reason of any negligence or omission of the Employer or the Maintenance Surveyor or the Maintenance Surveyor’s Representative in supervising or controlling the Contractor’s site operations or methods of working or temporary works, or in detecting or preventing or remedying defective work, or in ensuring proper performance or any other obligation of the Contractor, but subject always to the Employer’s liability to indemnify the Contractor in connection with the matters set out in the proviso to sub- clause (2) of this clause. |
| --- |
| Design responsibility | 25. Expect as may be provided for in the Contract, the Contractor shall not be responsible for the design of the permanent work or for the design of any Temporary Works designed by the Maintenance Surveyor. |
| Interference with traffic and adjoining properties | 26. All operations necessary for the execution of the Works shall be carried on so as not to interfere unnecessarily or improperly with the convenience of the public or the access to , use and occupation of public or private roads or footpaths or access to properties whether in the possession of the Employer or of any other person and the Contractor shall save harmless and indemnify the Employer in respect of all claims, demands, proceedings, damages, costs, charges and expenses whatsoever arising out of or in relation to any such matters in so far as the Contractor is responsible therefor. |
| Remedy on failure to insure | 27. If the Contractor shall fail to effect and keep in force any insurance which he may be required to effect by any Special Condition of Contract then and in any such case the Employer may effect and keep in force any such insurance and pay such premiums as may be necessary for that purpose and such premiums shall be recoverable by the Employer from the Contractor. |
| Accident or injury to workmen | 28. The Employer shall not be liable for or in respect of any damages or compensation payable at law in respect of or in consequence of any accident or injury to any workman or other person in the employment of the Contractor or any sub-contractor save and except an accident or injury resulting from any act or default of the Employer, his agents or employees and the Contractor shall indemnify and keep indemnified the Employer against all such damages and compensation, save and except as aforesaid and against all claims, demands, proceedings, costs, charges and expenses whatsoever in respect thereof or in relation thereto. |
| Contractor to give notice of injury |

29.	In the event of any workman or other person employed on the Works or in connection with the Contract whether in the employ of the Contractor or a sub-contractor suffering any personal injury and whether there be a claim for compensation or not, the Contractor shall, without delay, notify the Commissioner for Labour in such form as the Commissioner for Labour may require and shall forward two copies of such notification to the Maintenance Surveyor.

Patent rights and royalties

30.	The Contractor shall indemnify the Employer from and against all claims and proceedings for or on account of infringement of any patent rights, design, trademark or name or other protected rights in respect of any Constructional Plant, machine, work method or material or anything whatsoever required for the Works and from and against all claims, demands, proceeding, damages, costs, charges and expenses whatsoever in respect thereof or in relation thereto.  Except when otherwise specified in the Contract the Contractor shall pay all tonnage and other royalties, rent and other payments or compensation, if any for getting stone, sand, gravel, clay or other materials required for the Works.

Provided that where in compliance with the Contract or the Maintenance Surveyor’s written instructions the Contractor shall incorporate into the permanent work any patented article, process or invention, the Contractor shall be reimbursed by the Employer for all costs or damages which the Contractor may have had to pay to the persons entitled to such patented article, process or invention in respect of any infringement of any patent rights, design, trademarks, name or other protected right in relation to such article, process or invention.

| Provided further that the Contractor shall notify the Maintenance Surveyor as soon as the Contractor is aware of any incorporation of patented articles, processes or inventions as a condition precedent to any such reimbursement. |
| --- |
| Giving of notices and payment of fees | 31. The Contractor shall give all notices and pay all fees required to be given or paid by any enactment or any regulation or by-law of any local or other duly constituted authority in relation to the execution of the Works and by the rules and regulations of all public bodies and companies whose property or rights are affected or may be affected in any way by the Works and if any new fee is imposed or if any existing fee is increased after the date of submission by the Contractor of the Tender, all such new fees or increases shall be at the expense of the Contractor. |
| Compliance with enactments and regulations |

32.	The Contractor shall conform in all respects with:-

(a)	the provision of any enactment,

(b)	the regulations or by-laws of any local or duly constituted authority, and

(c)	the rules and regulations of such public bodies and companies as are referred to in Clause 			31,

| and any additions or amendment thereto during the continuance of the Works, which are applicable to the Works, and shall keep the Employer indemnified against all penalties and liabilities of every kind for breach of any such enactment, regulations, by-law or rules. |
| --- |
| Notices to be written in English and Chinese | 33. Any notice required to comply with any enactment or the rules and regulations of Government or other competent authority and which the Contractor may have to exhibit either for the benefit of the public or for the benefit of his employees shall be written in English and Chinese characters. |
| Site diary and labour returns |

34.	(1)	The Maintenance Surveyor’s Representative shall maintain a site diary for those Works nominated by the Maintenance Surveyor and he shall record daily in the site diary information with regard to labour, plant, materials, utilities, work carried out, and instructions issued to the Contractor and all other facts that may affect the progress or quality of the Works.

(2)	Where a site diary is maintained in accordance with subclause (1) of this Clause, an authorized agent or representative of the Contractor shall sign the site diary daily indication his agreement to the information recorded.  If the authorized agent or representative of the Contractor does not agree with any of the items recorded in the site diary he may draw reference to the points of disagreement in writing in the site diary.

| (3) The Contractor shall, as and when called upon to do so by the Maintenance Surveyor, make available to the Maintenance Surveyor or such other person as the Maintenance Surveyor may direct, such information as the Maintenance Surveyor considers necessary to enable him properly to keep and maintain his site record, but in any event and without prejudice to the generality of the foregoing, the Contractor shall deliver to the office of the Maintenance Surveyor’s Representative by not later than 1.00 p.m. on each working day a return in such form as the Maintenance Surveyor may prescribe showing in detail the numbers of the several classes of labour on the Site that day together with numbers of the several classes of labour so employed during the preceding twenty-four hours who were not included in the return for the previous day together with such information concerning materials, Constructional Plant and other such matters as Maintenance Surveyor may require. |
| --- |
| Fossils | 35. All fossils, coins, articles of value or antiquity and structures and other remains or things of geological or archaeological interest discovered on the Site shall, as between the Employer and the Contractor, be the absolute property of the employer and the Contractor shall take reasonable precautions to prevent his workmen or any other persons from removing or damaging any such article or thing and shall immediately upon discovery thereof and before removal acquaint the Maintenance Surveyor or the Maintenance Surveyor’s Representative of such discovery and carry out at the expense of the Employer the orders of the Maintenance Surveyor as to the disposal of the same. |
| Facilities for other contractors |

36.	(1)	The Contractor shall in accordance with requirements of the Maintenance Surveyor afford all reasonable facilities to the workmen of the Employer and for all other contractors employed by the Employer, and their workmen and of any utility undertaking or other duly constituted authority who may be carrying out, on or adjacent to the Site, any work not included in the Contract.

| (2) If however the Contractor shall on the written request of the Maintenance Surveyor either make available to the workmen of the Employer or to such other contractors and their workmen or to any such utility undertaking or authority, any road or way for the maintenance of which the Contractor is responsible, or permit the use by any of the foregoing of any of the Constructional Plant on the site or provide any other service of whatsoever nature for any of the foregoing, the Employer shall pay to the Contractor in respect of such use or service such sum as shall be certified for payment by the Maintenance Surveyor as reasonable. |
| --- |
| Clearance of the Site on completion | 37. As soon as practicable after the issue of the Certificate of Completion as provided for in Clause 56 the Contractor shall clear away and remove from the Site all surplus materials and rubbish of any kind whatsoever and leave the whole of the Site and the Works in a clean and workmanlike condition. |
| Publication of photographs of the Site or the Works | 38. (1) The Contractor shall not publish or otherwise circulate photographs of the Site or of the Works or any part thereof or anything therein except with the permission in writing of the Employer. |
| Offering gratuities |

39.	If the Contractor or any of his agents or employees shall be found to have offered or given any advantage, gratuity, bonus, discount, bribe or loan of any sort to any agent or employee of the Employer or to the Maintenance Surveyor or to any member of the Maintenance Surveyor’s staff, the Employer shall be at liberty forthwith to terminate the employment of the Contractor under the Contract, and to hold the Contractor liable for any loss or damage which the Employer may thereby sustain.

|  | LABOUR |
| --- | --- |
| Site cleanliness | 40. The Contractor shall keep the whole of the Site in a clean and sanitary condition and when so required by the Maintenance Surveyor the Contractor shall provide and maintain efficient and sanitary latrine accommodation for the use of all persons on the Site. |

Engagement of labour

Fairwages

41.	(1)	The Contractor shall make his own arrangements in regard to the provision of such labour, skilled and unskilled, as may be required for the execution of the Works and shall use all diligence in arranging for a sufficient and suitable supply of such labour but all such arrangements shall be in accordance with general local usage and subject to such regulations as Government may from time to time require to be observed.

(2)	As far as practicalbe all labour both skilled and unskilled shall be engaged in Hong Kong.

42.	(1)	The Contractor shall pay rates of wages and observe hours and conditions of labour which are not less favourable than the general level of wages, hours and conditions observed by other employers whose general circumstances in the trade or industry in which the Contractor is engaged are similar.

(2)	The Contractor shall in respect of all persons employed by him, whether in carrying out this Contract or otherwise, in every workshop or other place occupied or use by him for carrying out the Works comply with the general conditions required by this Clause.

(3)	The Contractor shall be responsible for the observance of this Clause by sub-contractors employed in the carrying out of the Works.

(4)	In the event of default being made in the payment of any money in respect of wages of any person employed by the Contractor in and for carrying out this Contract and if a claim therefor is filed in the office of the Department of Labour and proof thereof is furnished to the satisfaction of the Commissioner for Labour, Hong Kong, the Employer may, failing payment of the said money by the Contractor, make payment of such claim on behalf of the Contractor to the said Commissioner or his representative and any sums so paid shall be recoverable by the Employer form the Contractor.

Passes

43.	(1)	The Maintenance Surveyor may arrange the issue of passes to the Contractor for the admission of workpeople to the Site or to any Portion or Part thereof and in such event any person who fails to show his pass on demand to any duly authorized person may be refused admission.

(2)	If required by the Maintenance Surveyor the Contractor shall submit a list of the names of all his workpeople requiring passes together with two photographs of each person and shall satisfy the Maintenance Surveyor of their bona fides and identity.

(3)	Any pass so issued shall be returned at any time on the demand of the Maintenance Surveyor and in any case on completion of the Works or on cessation of the bearer’s employment on the Works.

|  | MATERIALS AND WORKMANSHIP |
| --- | --- |
| Quality of materials and workmanship and tests |

44.	(1)	All materials and workmanship shall be of the respective character, quality or kind required by the Contract and shall be subjected to such examinations, measurements or tests as the Contract shall require or as ordered by the Maintenance Surveyor or the Maintenance Surveyor’s Representative.

(2)	The Contractor shall provide such assistance, instruments, machines, labour and other facilities as may be necessary for examining, measuring or testing any work and the quality, weight or quantity of any material used and, before incorporation into the Works, shall supply for examining, measuring or testing such samples of materials as may be selected or required by the Maintenance Surveyor or the Maintenance Surveyor’s Representative.

(3)	The expense of complying with requirements of sub-clause (2) of this Clause, including any transportation costs, shall be borne by the Contractor in so far as the Contract provides for such examinations, measurements or tests, but if the Contract does not so provide, then the expense shall be valued in accordance will Clause 64 and certified for payment by the Maintenance Surveyor.

Provided that:-

(a)	such expense relating to any such examination, measurement or test not provided for in the Contract ordered by the Maintenance Surveyor that shows the materials or workmanship not to be in accordance with the Contract or with the Maintenance Surveyor’s instructions shall be borne by the Contractor;

(b)	in any series of tests made on any part of the Works the results of which indicate that in the opinion of the Maintenance Surveyor the Contractor has failed to comply with the requirements of the Contract, then the expense of complying with the requirements of this Clause shall be borne by the Contractor notwithstanding there being satisfactory individual tests included in any such series of tests.

| (c) In the event that any test or any series of tests show that the Contractor has failed to comply with the requirements of the Contract the Contractor shall propose and carry out at his own expense further or any other tests as the Maintenance Surveyor may approve. |
| --- |
| Access to the Site and places of manufacture | 45. The Maintenance Surveyor and any person authorized by him shall at all times have access to the Works and to the Site and to all workshops and places where materials or manufactured articles are being stored or prepared or from where materials or manufactured articles are being supplied by the Contractor or any sub-contractor, and the Contractor shall render every assistance to the Maintenance Surveyor and any person so authorized by him to obtain access when required to such other workshops and places from where materials or manufactured articles are being obtained for incorporation into the Works. |
| Examination of work before covering up |

46.	(1)	No work shall be covered up or put out of view without the approval of the Maintenance Surveyor or the Maintenance Surveyor’s Representative and the Contractor shall afford full opportunity for the Maintenance Surveyor or the Maintenance Surveyor’s Representative to examine and measure any work which is about to be covered up or put out of view and to examine any foundation before permanent work is placed thereon.

(2)	The Contractor shall give adequate notice to the Maintenance Surveyor or the Maintenance Surveyor’s Representative whenever any such work or foundation is ready for examination and the Maintenance Surveyor or the Maintenance Surveyor’s Representative shall, without unreasonable delay and unless he considers it unnecessary and advises the Contractor accordingly, attend for the purpose of examining and measuring such work or of examining any such foundation.

Uncovering and making openings

47.	(1)	The Contractor shall uncover any part of the Works or make such openings in or through the same as the Maintenance Surveyor may from time to time direct and shall reinstate and make good any such part in accordance with the Contract.

(2) If any such part has been covered up or put out of view after compliance with the requirements of Clause 46 and is found to be executed in accordance with the Contract, the expense of uncovering, making openings in or through, reinstating and making good the same shall be valued in accordance with Clause 64 and certified for payment by the Maintenance Surveyor but in any other case the expense shall be borne by the Contractor.

Removal of unsatisfactory material and work

48.	(1)	The Maintenance Surveyor or the Maintenance Surveyor’s Representative shall during the progress of the Works have the power to order in writing:-

(a)	the removal from the Site within such time as may be specified in the order of any material which is not accordance with the Contract,

(b)	the substitution of proper and suitable material and

(c)	the removal and proper re-execution, notwithstanding any previous examination, measurement or test thereof  or any interim payment therefor, of any work which, in respect of materials or workmanship, is not in accordance with the Contract.

(2)	The Contractor shall bear the expense of uncovering, breaking up and removal from the Site of any material or work not in accordance with the Contract and the Contractor shall also bear the expense of reinstating and making good all consequential damage to the Works resulting from such uncovering, breaking up or removal.

(3)	Where the rectification of any work or replacement of any material by the Contractor which does not comply with the Contract, would involve the removal and re-execution of the original permanent work the Maintenance Surveyor may but shall not be obliged to give directions for a variation of the Works in lieu of such removal and re-execution at no additional expense to the Employer.

Provided that if in the opinion of the Maintenance Surveyor such variation has involved the Contractor in expense in excess of that which would have been involved in the removal and re-execution of the original permanent work then the Maintenance Surveyor shall value in accordance with Clause 64 and certify for payment such excess.

|  | COMMENCEMENT COMPLETION AND DELAYS |
| --- | --- |
| Commencement of the Works |

49.	(1)	The Contractor shall commence any Works Order issued under the Contract on the date stated on such Works Order or if the date is not stated then within a reasonable time and shall proceed with the same with due diligence and without delay except as may be expressly sanctioned or ordered by the Maintenance Surveyor or be wholly beyond the control of the Contractor.  The Contractor shall not commence any Works without a Works Order.

(2) In the event that the Contractor is ordered to carry out Emergency Work, such work shall be commenced immediately unless otherwise instructed by the Maintenance Surveyor. All Emergency Work shall be carried out continuously by the Contractor working 24 hours a day unless otherwise instructed by the Maintenance Surveyor. Such Emergency Work may be ordered verbally and confirmed by a Works Order.

Occupation of the Site

50.	(1)	Save in so far as the Contract, any Works Order, or the Maintenance Surveyor may require, the extent of Portions of the Site of which the Contractor is to be given access and limited occupation, shall be sufficient to enable the Contractor to commence and proceed with the execution of the Works as provided in Clause 16 or where applicable on the date provide in the Works Order and otherwise in accordance with such reasonable proposals in writing as the Contractor shall make to the Maintenance Surveyor.  The Employer will from time to time, as such work proceeds, give to the Contractor limited occupation of such further parts of the Site as may be required to enable the Contractor to proceed with due despatch.

(2)	Every possible opportunity will be given to the Contractor by the Employer to take such limited occupation of the Site or such Portion thereof as is necessary for the execution of any Works Order but the employer reserves the right to use for any purpose the Site or Portion upon which works are in progress at any time.  The Contractor shall not be entitled to any costs arising from any disruption as a result of the limited occupation granted or use of the Site or Portion.

(3)	The Contractor shall bear all expenses and charges for special or temporary wayleaves required by him in connection with access to the Site.

(4) The access and limited occupation of the Site referred to in this clause shall not be exclusive to the Contractor but only such as shall enable him to execute the Works.

Time for completion

51.	(1)	Subject to any requirement stated on a Works Order as to completion of any Section of a Works Order before completion of the whole, the whole shall be completed within the time(s) stated on the Works Order, or if the time is not stated then within a reasonable time subject to provisions for extension of time contained in Clause 53 hereinafter.

(2)	Subject to any provision to the contrary contained in the Contract or Works Order none of the work shall, save as hereinafter provided, be carried on outside Normal Working Hours without the permission in writing of the Maintenance Surveyor save when work is unavoidable or absolutely necessary for:(

(a)	preventing injury to any person or saving the life of any person; or

(b)	preventing damage to property where the immediate carrying out of such work is necessary in order to prevent damage to that property(

in which case the Contractor shall immediately advise the Maintenance Surveyor.

(3)	Subject to compliance with clause 32 the Contractor may carry on any work on any General Holiday:(

Provided always that the Maintenance Surveyor may in his absolute discretion by notice, order the Contractor not to carry on any work on any General Holiday and/or after 1.00 p.m. on any Saturday and where such a notice is given any such period shall not be included in the time for completion.

(4)	General Holidays shall be included in the time for completion unless otherwise stated in the Contract.

| (5) The Contractor shall not be entitled to any additional payment for complying with the time requirements stated in the Works Order except payment at overtime rates when specified in the Works Order and then at the rates detailed in the Schedule of Rates. |
| --- |
| Continuous or Overtime Working | 52. The Maintenance Surveyor may, by written order, require the Contractor to execute any Works Order or Portion thereof, at any time of the day or night, or on a continuous basis, 24 hours per day. |
| Extension of time for completion |

53.	(1)	(a)	As soon as practicable but in any event within 42 days of the cause of any delay to the progress of the Works Order becoming apparent, the Contractor shall give notice in writing to the Maintenance Surveyor of the cause and probable extent of the delay.

Provided that as soon as it becomes apparent to the Contractor that any order or instruction issued by the Maintenance Surveyor is likely to cause a delay to the progress of the Work detailed in the Works Order the Contractor shall forthwith give notice in writing to the Maintenance Surveyor and specify the probable effect and extent of such delay.

(b)	If in the opinion of the Maintenance Surveyor the cause of the delay is:-

(i)	inclement weather conditions adversely affecting the progress of the Works, or

(ii)	the hoisting of storm signal no. 8 or above, or

(iii)	an instruction issued by the Maintenance Surveyor under Clause 5, or

(iv)	a variation ordered under Clause 63, or

(v)	a substantial increase in the quantity of any item of work included in the Works Order not resulting from a variation ordered under  Clause 63, or

(vi)	the Contractor not being given occupation of the Site or any Portion or part thereof in accordance with the Contract, or

(vii)	a disturbance to the progress of the Works which the Contractor could not reasonably have foreseen and for which the Employer or the Maintenance Surveyor is responsible or partially responsible, or

(viii)	the Maintenance Surveyor suspending the Works in accordance with Clause 57 in so far as the suspension is not occasioned by the circumstances described in Clause 57 (2) (a) to (d), or

(ix)	any utility undertaking or other duly constituted authority failing to commence or to carry out in due time any work directly affecting the execution of the Works, provided that the Contractor has taken all practical steps to cause the utility undertaking or duly constituted authority to commence or to proceed with such work, or

(x)	any other special circumstance of any kind whatsoever,

then the Maintenance Surveyor shall within a reasonable time consider whether the  Contractor is fairly entitled to an extension of time for the completion of the work detailed in the Works Order.

(c)	Notwithstanding the powers of the Maintenance Surveyor under the provisions of this Clause to decide whether the Contractor is fairly entitled to an extension of time the Contractor shall not be entitled to an extension of time for the completion of the Work detailed in the Works Order if the cause of the delay is:-

(i)	the failure of a Nominated Sub-contractor to commence or to carry out work in due time which the Contractor has not, in the opinion of the Maintenance Surveyor, taken all practical steps to prevent, or

(ii)	a suspension occasioned by the circumstances described in Clause 57 (2)(a) to (d), or

(iii) a shortage of Constructional Plant or labour.

(2)	If in accordance with sub-clause (1) of this Clause the Maintenance Surveyor decides that the Contractor is fairly entitled to an extension of time for the completion of the work detailed in the Works Order, the Maintenance Surveyor shall within a reasonable time determine, grant and notify in writing to the Contractor such extension.  If the Maintenance Surveyor decides that the Contractor is not entitled to an extension, the Maintenance Surveyor shall notify the Contractor in writing accordingly.

Provided that the Maintenance Surveyor in determining any such extension shall take into account all the circumstances known to him at that time, including the effect of any omission of work or substantial decrease in any item of work.

Provided further that the Maintenance Surveyor shall, if the Contractor shall so request in writing, make a subsequent review of the circumstances causing delay and determine whether any further extension of time for completion should be granted.

(3)	For the purposes of determining whether or to what extent the Contractor may be entitled to an extension of time under sub-clause (1)(b) of this Clause the Maintenance surveyor may require the Contractor to submit full and detailed particulars of the cause and extent of the delay to the progress of the work detailed in the Works Order.  Where such full and detailed particulars are required by the Maintenance Surveyor, they shall be submitted in writing by the Contractor to the Maintenance Surveyor as soon as practicable in order that the Contractor’s claim may be investigated at the time by the Maintenance Surveyor.  If the Contractor fails to comply with the provisions of this sub-clause, the Maintenance Surveyor may consider such extension only to the extent that the Maintenance Surveyor is able on the information available.

(4) Any extension of time granted by the Maintenance Surveyor to the Contractor shall, except as provided elsewhere in the Contract, be deemed to be in full compensation and satisfaction for any loss or injury sustained or sustainable by the Contractor in respect of any matter or thing in connection with which such extension shall have been granted and every extension shall exonerate the Contractor from any claim or demand on the part of the Employer for any delay during the period of such extension but not for any delay continued beyond such period.

Rate of progress

54.	(1)	If the rate of progress of the Works or any Section thereof is at any time in the opinion of the Maintenance Surveyor too slow to ensure completion by the prescribed time or extended time for completion, the Maintenance Surveyor may so inform the Contractor in writing and the Contractor shall immediately take such steps as are necessary to expedite the completion of the Works or any Section thereof.  The Contractor shall inform the Maintenance Surveyor of such proposed steps.

(2)	Notwithstanding the provisions of sub-clause (1) of this Clause and subject to compliance with any enactment, regulation or by-law, the Maintenance Surveyor shall be empowered to instruct the Contractor in writing to carry out the Works or any part thereof during any hours of the day where the Maintenance Surveyor considers it necessary owing to the default, negligence, omission or slow progress of the Contractor.

(3) The Contractor shall not be entitled to any additional payment for complying with any instruction given in accordance with this Clause.

Liquidated damages for delay

55.	(1)	If the Contractor shall fail to complete a Works Order within the time prescribed by Clause 51 or extended time, then the Contractor shall pay to the Employer a sum equal to ten per cent of the estimated value of the Works Order as determined by the Maintenance Surveyor at time of issue of the Works Order divided by the time for completion in days prescribed in the Works Order including General Holidays as liquidated damages for such default and not as a penalty for every day or part of a day which shall elapse between the time prescribed by Clause 51 or extended time as the case may be and the date of completion of the Work Order.

(2)	The Employer may without prejudice to any other method of recovery deduct the amount of such damages from any monies due or which may become due to the Contractor under this or any other contract.

(3)	The Payment or deduction of such damages shall not relieve the Contractor of his obligation to complete the Works Order or of any other of his obligations and liabilities under the Contract.

(4)	If before the completion of the whole of the Works Order any part of the Works Order has been certified by the Maintenance Surveyor as completed pursuant to Clause 56 the liquidated damages for delay shall for any period of delay after such certification be reduced in the proportion which the value of the part so certified bears to the value of the whole of the Works Order.

(5) If upon a subsequent review of the circumstances causing delay the Maintenance Surveyor shall grant an extension or further extensions of time, the Employer shall no longer be entitled to liquidated damages in respect of the period of such extension of time. Any sum in respect of such period which may have been paid or deducted pursuant to this clause shall be reimbursed to the Contractor together with interest at the rate provided for in Clause 82 within 28 days of the date that such extension is granted.

Completion of the Works

56.	(1)	When the work detailed in a Works Order has been substantially completed and has passed any final test that may be prescribed by the Contract the Contractor may notify the Maintenance Surveyor to that effect and give an undertaking to carry out any outstanding work during the Maintenance Period and requesting the Maintenance Surveyor to issue a Certificate of Completion.  The Maintenance Surveyor shall, within 21 days of the date of receipt of such notice either:-

(a)	issue a Certificate of completion stating the date on which, in the Maintenance Surveyor’s opinion, the Works were substantially completed in accordance with the Contract and the Maintenance Period shall commence form the date stated in such certificate, or

(b)	give instruction in writing to the Contractor specifying all the work which, in the Maintenance Surveyor’s opinion, is required to be done by the Contractor before such certificate can be issued, in which case the Contractor shall not be permitted to make any further request for a Certificate of Completion and the provisions of sub-clause (2) of this clause shall apply.

(2)	Notwithstanding the provisions of sub-clause (1) of this Clause, as soon as in the opinion of the Maintenance Surveyor the Works have been substantially completed and passed any final test which may be prescribed by the Contract, the Maintenance Surveyor shall issue a Certificate of Completion in respect of the Works and the Maintenance Period shall commence from the date of completion stated in such certificate.

(3)	The Contractor shall complete any outstanding work as soon as reasonably practicable after the issue of the Certificate of Completion or as directed by the Maintenance Surveyor and in any event before the expiry of the Maintenance Period.  The Contractor’s obligation to provide, service and maintain site offices, latrines and the like, shall continue for as long as may be necessary for the completion of any outstanding work.

(4)	The provision of sub-clause (1), (2) and (3) of this Clause shall apply equally to any Section.

(5)	(a)	The Maintenance Surveyor shall give a Certificate of Completion in respect of any part of the Works which has been completed to the satisfaction of the Maintenance Surveyor and is required by the Employer for permanent occupation or use before the completion of the whole of the Works or any Section.

(b)	The Maintenance Surveyor, following a written request from the Contractor, may give a Certificate of Completion in respect of any substantial part of the Works which has been completed to the satisfaction of the Maintenance Surveyor before the whole of the Works or any Section and is capable of permanent use by the Employer.

(c)	when a Certificate of Completion is given in respect of a part of the Works such part shall be considered as completed and the Maintenance Period for such part shall commence from the date of completion stated in such certificate.

(6)	Any Certificate of Completion given in accordance with this Clause in respect of any Section or part of the Works shall not be deemed to certify completion of any ground or surfaces requiring reinstatement unless the certificate shall expressly so state.

(7)	For the purposes of this Clause the term “Works” shall exclude any work executed in accordance with Clause 59(2).

|  | SUSPENSION OF THE WORKS |
| --- | --- |
| Suspension of the Works |

57.	(1)	The Contractor shall upon the written order of the Maintenance Surveyor suspend the progress of the Works or any part thereof for such time or times and in such manner as the Maintenance Surveyor may consider necessary and shall during such suspension properly protect and secure the Works so far is necessary in the opinion of the Maintenance Surveyor.

(2)	If upon written application by the Contractor to the Maintenance Surveyor, he is of the opinion that the Contractor has been involved in additional expenditure by reason of a suspension order given under this Clause then the Maintenance Surveyor shall ascertain the Cost incurred and certify for payment accordingly unless such suspension order is:-

(a)	otherwise provided for in the Contract, or

(b)	necessary by reason of weather conditions affecting the safety or quality of the Works or any part thereof, or

(c)	necessary by reason of some default on the part of the Contractor, or

(d) necessary for the proper execution of the Works or for the safety of the Works or any part thereof in as much as such necessity does not arise form any act or default of the Maintenance Surveyor or the Employer or from any of the excepted risks defined in Clause 23.

Suspension lasting more than 90 days

58.	If the progress of the Works or any part thereof is suspended on the written order of the Maintenance Surveyor and if permission to resume work is not given by the Maintenance Surveyor within a period of 90 days after the date of suspension then the Contractor may, unless such suspension is occasioned by the circumstances described in Clause 57(2)(a) to (d), serve a notice in writing on the Maintenance Surveyor requiring permission within 28 days after the receipt of such notice to proceed with the Works or that part thereof in regard to which progress is suspended.  If within the said 28 days the Maintenance Surveyor may, but is not bound to, elect to treat the suspension where it affects part only of the Works as an omission of such part under Clause 63 or where if affects the whole of the Works as an abandonment of the Contract by the Employer.

|  | MAINTENANCE AND DEFECTS |
| --- | --- |
| Execution of work of repair |

59.	(1)	The Works shall at or as soon as practicable after the expiry of the Maintenance Period be delivered up to the Employer in the condition required by the Contract, fair wear and tear excepted.

(2)	During the Maintenance Period or within 14 days after its expiration, the Maintenance Surveyor may by notice in writing require the Contractor to carry out maintenance work including any work of repair or rectification, or make good any defect, imperfection, shrinkage, settlement or other fault identified within the Maintenance Period, and the Contractor shall carry out such work within the Maintenance Period or as soon as practicable thereafter.

(3)	All such work shall be carried out by the Contractor at his own expense if the necessity for such work shall be due to the use of materials or workmanship not in accordance with the Contract or to neglect or failure on the part of the Contractor to comply with any obligation expressed or implied on the Contractor’s part under the Contract.  If in the opinion of the Maintenance Surveyor such necessity shall be due to any other cause, the works shall be valued and certified as if it were a variation order in accordance with Clause 63.

(4) If the Contractor fails to execute any outstanding works as required by Clause 56(3) or fails to execute any work which the Maintenance Surveyor requires the Contractor to carry out in accordance with this Clause the Employer shall be entitled after giving reasonable notice in writing to the Contractor, to have such work carried out by his own workmen or by other contractors and if such work is work which the Contractor would have been required to carry out at his own expense the Employer shall be entitled to recover from the Contractor the cost incurred in connection therewith.

Temporary reinstatement

60.	If in the course or for the purpose of the execution of the Works or any part thereof any highway or other road or way shall have been broken into then notwithstanding any other provision of the Contract:-

(a)	if the permanent reinstatement of such highway or other road or way is to be carried out by the appropriate authority or by some person other than the Contractor, the Contractor shall at his own expense and independently of any requirement of or notice from the Maintenance Surveyor be responsible for the making good of any subsidence or shrinkage or other defect, imperfection, settlement or fault in the temporary reinstatement of such highway or other road or way and for the execution of any necessary repair or amendment thereof from whatever cause the necessity arises until the end of the Maintenance Period in respect of the Works beneath such highway or other road or way or until the authority or other person as aforesaid shall have taken full occupation of the Site for the purpose of carrying out permanent reinstatement, whichever is the earlier.  The Contractor shall indemnify the Employer against and from any damage or injury to the Employer or to the third parties arising out of or in consequence of any neglect or failure of the Contractor to comply with the foregoing obligations or any of them and against and from all claims, demands, proceedings, damages, costs, charges and expenses whatsoever in respect thereof or in relation thereto;

(b)	as from the end of such Maintenance Period or the taking of full occupation as aforesaid, whichever is the earlier, the Employer shall indemnify the Contractor against and from any damage or injury as aforesaid arising out or in consequence of or in connection with the with the said permanent reinstatement or any defect imperfection or failure of or in such work of permanent reinstatement and against and from all claims, demands, proceedings, damages, costs, charges and expenses whatsoever in respect thereof or in relation thereto;

(c) where the authority or other person as aforesaid shall take full occupation of the Site as aforesaid in Portions the responsibility of the Contractor under paragraph (a) of this Clause shall cease in regard to any such Portions at the time full occupation thereof is so taken but shall during the continuance of the said Maintenance Period continue in regard to any Portion of which full occupation has not been so taken and the indemnities given by the Contractor and the Employer respectively under paragraphs (a) and (b) of this Clause shall be construed and have effect accordingly.

Investigating defects

61.	(1)	At any time prior to the issue of the Maintenance Certificate in accordance with Clause 86 the Contractor shall, if instructed by the Maintenance Surveyor in writing, investigate the cause of any defect, imperfection or fault under the directions of the Maintenance Surveyor.

Provided that if the Maintenance Surveyor at his absolute discretion so decides, the Employer shall be entitled, after giving reasonable notice in writing to the Contractor, to have such investigation carried out by his own workmen or by other contractors and the provisions of sub-clauses (2) and (3) of this Clause shall apply to any investigation so carried out.

(2)	If such defect, imperfection or fault shall be one for which the Contractor is liable in accordance with the provisions of the Contract, the expense incurred investigating as aforesaid shall be borne by the contractor and he shall in such case repair, rectify and make good such defect, imperfection or fault together with any consequential damage at his own expense.

(3)	If such defect, imperfection or fault shall be one for which the Contractor is not so liable, the any investigation and remedial work carried out by the Contractor as aforesaid shall be valued in accordance with Clause 64 and certified for payment by the Maintenance Surveyor.

|  | MEASUREMENT, VARIATIONS, VALUATIONS AND CLAIMS |
| --- | --- |
| Measurement of Works | 62. Except as otherwise stated all Works executed under each Works Order shall be measured by the Contractor in accordance with the Schedule of Rates during the progress of as soon as possible after the completion of each Works Order. The Contractor shall give full facilities to the Maintenance Surveyor to take independent measurements of all or part of such Works. The Contractor shall give due notice to enable the Maintenance Surveyor to be present when the Contractor is measuring such Works. |
| Order for Variation |

63.	(1)	The Maintenance Surveyor shall have the power to make any variation in the form, character or quality of any work or materials detailed in the Specification or the Schedule of Rates, or to order different work or material of any kind which is not detailed in the Specification or Schedule of Rates and no such variation or order for different work or material shall in any way vitiate or invalidate the Contract.

(2)	The Maintenance Surveyor shall also have the power to make any variation in the form, character, quality or quantity of any work or materials ordered under any Works Order by means of issuing a written and signed Variation Order.  A Variation Order shall be deemed to be an integral and indivisible part of Works Order which it varies.

Such variations may include additions, omissions, substitutions, alterations, changes in quality, form, character, kind, position, dimension, level or line.

(3)	No variation shall be made without an order in writing from the Maintenance Surveyor.

Provided that:-

(a)	if for any reason the Maintenance Surveyor shall consider it desirable to give any such order verbally the Contractor shall comply with such an order and confirmation in writing of such verbal order given by the Maintenance Surveyor shall be issued within 3 working days after such verbal order.

(b) if the Contractor shall confirm in writing to the Maintenance Surveyor any verbal order of the Maintenance Surveyor and such confirmation shall not be contradicted in writing by the Maintenance Surveyor before the commencement of the work concerned.

Valuing Variations

64.	(1)	The rate for any work or material which is varied in form, character or quality from that detailed in the Specification or Schedule of Rates or for any different work or material of any kind ordered which is  not detailed in the Specification or Schedule of Rates shall be agreed upon between the Maintenance Surveyor and the Contractor in accordance with the rules contained in the Schedule of Rates.

(2) In the event of the Maintenance Surveyor and the Contractor failing to reach agreement on any rate under the provisions of sub-clause (1) of this Clause, the Maintenance Surveyor shall fix such rate as shall in his opinion be reasonable and notify the Contractor accordingly.

Daywork

65.	(1)	The Maintenance Surveyor may, if in his opinion it is necessary or desirable, order in writing that any work to be carried out as a result of a variation ordered under Clause 63 shall be executed on a daywork basis.

(2)	The Contractor shall then be paid for such work under the conditions and at the rates set out in the Contract or if no such conditions and rates have been included, at such rates as the Maintenance Surveyor shall determine as being reasonable.

(3)	The Contractor shall furnish to the Maintenance Surveyor such receipts or other vouchers as may be necessary to prove the sums paid and before ordering materials shall if so required by the Maintenance Surveyor submit quotations for the same for his approval.

(4)	In respect of all work executed on a daywork basis the Contractor shall during the continuance of such work deliver each working day to the Maintenance Surveyor’s Representative a list, in duplicate, of the names and occupations of and time worked by all workmen employed on such work on the previous working day and a statement, also in duplicate, showing the descriptions and quantity of all materials and Constructional Plant used thereon or therefor.  One copy of such lists and statements shall be agreed as correct or be rejected with stated reasons, and be signed by the Maintenance Surveyor’s Representative and returned to the Contractor within 2 days exclusive of General holidays.

(5)	At the end of each month the Contractor shall deliver to the Maintenance Surveyor’s Representative a priced statement of the labour, materials and Constructional Plant used on a daywork basis.

Provided that if the Maintenance Surveyor shall consider that for any reason the sending of such statement by the Contractor in accordance with the foregoing provision was impracticable the Maintenance Surveyor shall nevertheless be entitled to authorize payment for such work either as daywork, on being satisfied as to the time employed and the Constructional Plant and materials used thereon, or at such value as shall in the Maintenance Surveyor’s opinion be reasonable.

(6) The Contractor shall inform the Maintenance Surveyor’s Representative in advance when-ever the Contractor proposes to carry out daywork ordered by the Maintenance Surveyor and shall afford every facility for the Maintenance Surveyor’s Representative to check all time and materials for which the Contractor proposes to charge.

Disturbance of the progress of the Works

66.	If upon written application by the Contractor to the Maintenance Surveyor the Maintenance Surveyor is of the opinion the Contractor has been or is likely to be involved in expenditure for which the Contractor would not be reimbursed by a payment made under any other provision in the Contract by reason of the progress of the Works or any part thereof having been materially affected by:(

(a)	the Contractor not having received in due time necessary instructions, decisions, Drawings, Specification, details or levels from the Maintenance Surveyor for which the Contractor specifically applied in writing on a date which, having regard to the time for completion of the Works prescribed by Clause 51 or to any extension of time then granted by the Maintenance Surveyor, was neither unreasonably distant from nor unreasonably close to the date on which it was necessary for the Contractor to receive the same, or

(b)	any variation ordered in accordance with Clause 63, or

(c)	the opening up for inspection in accordance with Clause 47 of any work covered up or the testing of materials or workmanship not required by the Contract but directed by the Maintenance Surveyor or the Maintenance Surveyor’s Representative in accordance with Clause 44(1) unless the inspection or test showed that the work, materials or workmanship were not in accordance with the Contract, or

(d)	delay caused by any person or any company, not being a utility undertaking, engaged by the Employer in supplying materials or in executing work directly connected with but not forming part of the Works, or

(e)	late delivery of material, plant or equipment by the Employer, or

(f)	changes in the sequence, method or timing of construction, order of work which are specified in the Works Order, or

(g)	changes to the ingress or egress to any work,

then the Maintenance Surveyor shall ascertain the Cost incurred and certify for payment accordingly.

Notice of claims

67.	(1)	If the Contractor intends to claim a higher rate than one notified to him by the Maintenance Surveyor pursuant to sub-clause (2) of Clause 64 or sub-clause (2) of Clause 65 the Contractor shall within 28 days of such notification give notice in writing of his intention to claim to the Maintenance Surveyor.

(2)	If the Contractor intends to claim any additional payment under the provisions of any Clause of the General or Special Conditions of Contract other than as mentioned in sub-clause (1) of this Clause, the Contractor shall within 28 days of the occurrence of the event giving rise to the possible claim becoming apparent serve notice in writing on the Maintenance Surveyor of his intention to claim.

(3)	The Contractor shall keep such contemporary records as may reasonably be necessary to support any claim and shall give to the Maintenance Surveyor details of the records being kept in respect thereof.  Without necessarily admitting the Employer’s liability, the Maintenance Surveyor may instruct the Contractor to keep and agree with the Maintenance Surveyor’s Representative any additional contemporary records as are reasonable and may in the opinion of the Maintenance Surveyor be material to the claim.  The Contractor shall permit the Maintenance Surveyor and the Maintenance Surveyor’s Representative to inspect all records kept pursuant to this Clause and shall supply copies thereof as and when the Maintenance Surveyor or Maintenance Surveyor’s Representative shall so instruct.

(4)	After the giving of a notice to the Maintenance Surveyor under this Clause, the Contractor shall, as soon as is reasonable, send to the Maintenance Surveyor a first interim account giving full and detailed particulars of the sum claimed to-date and of the grounds upon which the claim is based. Thereafter, at such intervals as the Maintenance Surveyor may reasonably require, the Contractor shall send to the Maintenance Surveyor further up-to-date accounts giving the accumulated total of the claim together with full and detailed particulars of any further grounds upon which it is based.

(5)	If in the opinion of the Maintenance Surveyor the Contractor has not complied with the notice provisions contained in sub-clause (1) or (2) of this Clause in respect of any claim, such claim shall not be considered.  If the Contractor fails to comply with the provisions of sub-clause (3) or (4) of this Clause in respect of any claim the Maintenance Surveyor may consider such claim only to the extent that the Maintenance Surveyor is able on the information made available.

(6)	The Maintenance Surveyor shall not consider and the Employer shall not be liable to pay any claim unless as soon as reasonably possible after the notification by the contractor of his intention to claim under sub-clauses (1) or (2) of this Clause, but in any event within a period of 180 days from the certified date of completion of the Works Order the Contractor shall have given to the Maintenance Surveyor full and detailed particulars in writing of the circumstances giving rise to the claim, of the rate or sum claimed and of the manner in which such rate or sum is calculated.

Provided that when the Contractor’s claim relates to the whole of the Works under the Contract the period of 180 days shall commence on the certified date of completion of the final Works Order.

|  | NOMINATED SUB-CONTRACTORS |
| --- | --- |
| The employer’s right to order work or materials from specialists |

68.	(1)	The Employer reserves the right to order work to be executed or goods or materials to be supplied by any specialist, merchant, tradesman or other person notwithstanding the fact that relevant items for such work to be executed or goods or materials to be supplied are contained in the Schedule of Rates.

(2)	When instructed by the Maintenance Surveyor the Contractor shall enter into a sub-contract with the Nominated Sub-contractor using the appropriate standard form of sub-contract provided by the Employer.  Subject to Clause 69(1), the Contractor shall not enter into any other form of sub-contract with a Nominated Sub-contractor.

(3) If the services to be provided in the Nominated Sub-contract include any matter of design or specification of any part of the Works (other then Temporary Works) or of any equipment or plant to be incorporated therein, such design or specification requirement shall be stated in the Contract and shall be included in any such nominated sub-contract and the obligation of the Contractor in respect thereof shall be only that which has been stated in accordance with this Clause.

Varied form of sub-contract and objections to nomination

69.	(1)	The Maintenance Surveyor may instruct the Contractor to enter into a sub-contract with a Nominated Sub-contractor containing different terms from those specified in the standard form of sub-contract referred to in Clause 69(2).  If the Maintenance Surveyor so instructs the Contractor, then

(a)	the Contractor shall not be bound to discharge his obligations under the Contract to the extent that the terms of such sub-contract are inconsistent with the discharge of the same, and

(b)	in the event of the Contractor incurring additional expenditure due to the terms of such sub-contract being different from the terms of the standard form of sub-contract, so much of such expenditure as the Contractor could not reasonably avoid shall be ascertained by the Maintenance Surveyor and certified accordingly.

(2)	The Contractor shall not be obliged to enter into a sub-contract with a Nominated Sub-contractor against whom the contractor may raise any objection which the Maintenance Surveyor considers reasonable.  Unless such  objection shall be notified in writing to the Maintenance Surveyor within 14 days of the date of the Maintenance Surveyor’s instruction given under Clause 68(2) to enter into a sub-contract, the Contractor shall be obliged to enter into such sub-contract. If, pursuant to this sub-clause, the Contractor does not enter into a sub-contract, the Maintenance Surveyor shall either:

(a)	nominate an alternative sub-contractor in which case provisions of Clauses 68 and 69 shall apply; or

(b) by Variation Order given in accordance with Clause 63(2) vary the Works or the work, materials or services provided for in the Nominated Sub-contract including if necessary the omission of any such work, materials or services so that they may be provided by workmen or contractors employed by the Employer either concurrently with the Works, in which case the provisions of Clause 36 shall apply, or at some other date.

Payment to Nominated Sub-contractors

70.	(1)	The Contractor shall, when required by the Maintenance Surveyor, produce all quotations, invoices, vouchers and receipts in connection with expenditure in respect of Nominated Sub-contractors.

(2)	The amount which the Employer shall pay to the Contractor for work executed or goods and materials supplied by Nominated Sub-contractors shall be the net cost actually paid or to be paid by the Contractor to such Nominated sub-contractor as certified by the Maintenance Surveyor.

(3)	In addition the Employer shall pay to the contractor a percentage as detailed in the Contract on the net cost paid or to be paid to such Nominated Sub-Contractors by the Contractor, which percentage shall be deemed to be full payment for the Contractor’s profit, overhead expenses, provision of facilities and any other costs, charges and expense whatsoever arising out of or in connection with work executed or goods or materials supplied by such Nominated Sub-contractors.

(4)	The Contractor shall within 28 days of the delivery to the Employer of the Maintenance Surveyors certificate issued in accordance with Clauses 79, 80 or 81 hereafter, notify and pay in full to nominated Sub-contractors the amounts certified in such certificate to be due for work executed by Nominated Sub-contractors.

(5)	(a)	Before issuing any certificate under Clauses 79, 80 or 81 the Maintenance Surveyor shall be entitled to demand from the Contractor reasonable proof that all sums, included in previous certificates in respect of work executed, or materials or services supplied by Nominated Sub-contractors have been paid to each Nominated Sub-contractor.  If the Contractor has not made such payments the Contractor shall:(

(i)	give details to the Maintenance Surveyor in writing of the reason why the Contractor is withholding or refusing to make such payments, and

(ii)	produce to the Maintenance Surveyor reasonable proof that the Contractor has so informed every such Nominated Sub-contractor in writing.

(b)	If the Contractor fails to satisfy the Maintenance Surveyor that he has reasonable cause for withholding or refusing to make any payment to any Nominated Sub-contractor as aforesaid, the Employer, following notice in writing to the Contractor, shall be entitled:-

(i)	to pay any Nominated Sub-contractor direct, upon the certificate of the Maintenance Surveyor, all payments, which the Contractor has failed to make to any Nominated Sub-contractor and all such sums paid direct shall be recoverable by the employer from the Contractor and/or

(ii)	if satisfied that it is expedient to do so, to pay any Nominated Sub-contractor direct all payments that become due, for any work executed, or materials or services supplied in connection with the Works in so far as the price or cost thereof has not already been paid by the Contractor.

(c) Neither the existence nor the exercise of any of the aforesaid powers by the Employer or the Maintenance Surveyor shall render the Employer liable to pay any Nominated Sub-contractor directly.

Assignment of Nominated Sub-contractor’s obligations

71.	In the event of a Nominated Sub-contractor having undertaken towards the Contractor in respect of the work executed or the materials or services supplied by such Nominated Sub-contractor any continuing obligation extending for a period exceeding that of the Maintenance Period under the Contract, the Contractor shall immediately after the expiration of the Maintenance Period assign to the Employer the benefit of such obligation for the unexpired duration thereof.

|  | CONSTRUCTIONAL PLANT, TEMPORARY BUILDINGS AND MATERIALS |
| --- | --- |
| Vesting of Constructional Plant and temporary buildings | 72. All constructional Plant and temporary buildings owned by the Contractor shall when brought onto the Site be and become the property of the Employer but may be removed from the Site by the Contractor at any time unless removal is expressly prohibited by the Maintenance Surveyor in writing. Upon completion of the Works or removal as aforesaid or under the terms of Clause 94(2) such Constructional Plant and temporary buildings shall re-vest in the Contractor. |
| Vesting of materials | 73. All materials owned by the Contractor for incorporation in the Works shall become the property of the Employer upon delivery to the Site, and shall not be removed without an instruction or the prior written consent of the Maintenance Surveyor. Materials shall only re-vest in the Contractor to the extent that they may be found to be surplus to requirements upon or prior to completion of the Works. The operation of this Clause shall not be deemed to imply any approval by the Maintenance Surveyor of such materials or prevent the rejection by the Maintenance Surveyor of any material at any time. |
| Removal of Constructional Pant, temporary buildings and materials |

74.	(1)	Upon the issue of the Certificate of Completion under the Contract in respect of the final Works Order or, where appropriate, the issue of a Certificate of Completion for the Works comprised in an individual Works Order the Contractor shall remove all Constructional Plant, temporary building and surplus materials from the Site, except those required to complete any outstanding work in accordance with Clause 56 or to discharge the Contractor’s other obligations under the Contract.

(2)	If the Contractor shall fail to remove from the Site any Constructional Plant, temporary buildings or surplus materials as aforesaid within such reasonable time after completion of the Works as may be allowed by the Maintenance Surveyor, then the Employer may-

(a)	sell any such Constructional Plant owned by the Contractor, temporary buildings or surplus materials and after deducting from any proceeds of sale the charges and expenses of and in connection with such sale shall pay the balance, if any, to the Contractor but to the extent that the proceeds of sale are insufficient to meet all such charges and expenses the excess shall be recoverable by the Employer from the Contractor, or

(b) return Constructional Plant hired or the subject of a hire-purchase agreement to the firm or company from whom it was so hired by the Contractor, and recover the charges and expenses of and in connection with such return from the Contractor.

Hired and hire-purchase Constructional Plant

75.	Constructional Plant which is not solely owned by the Contractor shall not be brought onto the Site without the consent of the Maintenance Surveyor, and the Maintenance Surveyor shall have the power to withhold consent unless the owner of the constructional Plant gives a written undertaking to the Employer that-

(a)	the owner of the Constructional Plant will consent to the assignment by the Contractor to the Employer of the benefit of any hiring or hire-purchase or other agreement made with the Contractor in respect of the relevant plant in the event of either the forfeiture or termination of the Contract by the Employer in accordance with the provisions of the Contract or the abandonment of the Contract by the Contractor before completion of the Works.

| (b) subject to any assignment under (a) above, the owner of the Constructional Plant will permit the Employer, or any other contractor employed by the Employer, to use the relevant Constructional Plant for the purpose of completion of the Works. |
| --- |
| Employer’s expense in entering into hire or hire-purchase agreement | 76. In the event of the Employer entering into any agreement for hiring or hire-purchase under Clause 75 all sums paid by the Employer under the provisions of any such agreement and all expenses incurred by the Employer in entering into such agreement shall be deemed to be part of the cost of completing the Works, and shall be recoverable by the Employer from the Contractor. |
| Liability for loss or damage to Constructional Plant | 77. Save as stated in Clause 23, the Employer shall not at any time be liable for the loss of or damage to any of the Constructional Plant, temporary buildings or materials which have become the property of the Employer under Clauses 72 and 73 or loss of or damage to any hired or hire-purchase Constructional Plant brought onto the Site in accordance with Clause 75. |
| Incorporation of certain Clauses in sub-contracts |

78.	The Contractor shall when entering into any sub-contract for the execution of any part of the Works incorporate in such sub-contract the provisions of Clauses 72 to 77 and shall use his endeavours to ensure that they are observed.

|  | CERTIFICATES AND PAYMENTS |
| --- | --- |
| Submissions* for payment for the works | 79A. As soon as possible after completion of measurement of each Works Order, and in any case within 90 days of completion of the works executed under each Works Order, the Contractor shall submit to the Maintenance Surveyor for checking and any necessary correction three signed copies of a bill for the work executed under that Works Order and all further sums which the Contractor considers to be due to him under that Works Order. Such bills shall be prepared on forms supplied by and at the expense of the Contractor, set out in a manner which shall be determined by the Maintenance Surveyor and shall be complete with the supporting dimension book(s) and any vouchers, invoices, receipts, or other documents or information which the Maintenance Surveyor may require. After checking, any necessary correction and completion the Maintenance Surveyor shall certify on the bill such sum as is the correct value of the work executed under the Works Order and such further sum as may be due to the Contractor under that Works Order and pass this certificate to the Employer for payment to the Contractor. |
| Submissions* for payment for the works |

79B.	(1)	As soon as possible after completion of measurement of each Works Order, and in any case within 90 days of completion of the work executed under each Works Order, the Contractor shall submit to the Maintenance Surveyor for checking and any necessary correction signed dimension book(s) for the executed under that Works Order.  Should the Contractor fail to submit such signed dimension book(s) within the stipulated period of 90 days without due reason acceptable to the Maintenance Surveyor, the Maintenance Surveyor may value of the Work.  In this event the Maintenance Surveyor’s valuation shall be final, and 7.5% of the value of the work established by the Maintenance Surveyor shall be deducted before payment to the Contractor as payment of the Employer’s costs for so valuing.

(2)	Dimension book(s) shall be supplied by and at the cost of the Contractor, set out in a manner which shall be determined by the Maintenance Surveyor and when submitted they shall be accompanied by any supporting vouchers, invoices, receipts or other documents or information which the Maintenance Surveyor may require.

(3)	The dimensions of work completed pursuant to a Complaint Chit shall be endorsed by the Contractor on the reverse side of the said Complaint Chit or attached to the said Complaint Chit and when submitted for payment shall be accompanied by all supporting vouchers, invoices, receipts or other documents or information which the Maintenance Surveyor may require.  The Maintenance Surveyor may check the Complaint Chit submitted and subject to agreement with the Contractor on  any  corrections made, shall certify the value of work executed and shall pass such certificate for payment.

(4)	For works ordered on a Complaint Chit up to a standard base value of the amount stated in the Appendix to the Form of Tender the Contractor may claim the standard base charge without stating any details or measurements, subject to the Complaint Chit being received, duly and properly countersigned that the work has been acceptably carried out, by the Maintenance Surveyor’s Representative within 12 working days of issue.  Complaint Chits received after 12 working days from issue may, at the Maintenance Surveyor’s discretion, be referred back to the Contractor for measurement details and upon receipt thereof will be batched and if required sampled, checked and valued in accordance with (6) below.  If details and measurements are stated on the complaint Chit in accordance with (3) above these will be at the Maintenance Surveyor’s discretion either individually checked and valued or batched and sample checked and valued and the Contractor will only be paid the value arrived at, whether below the standard base charge or not.

(5)	Completed Works Orders will be sorted by the Maintenance Surveyor according to the claimed value of each separate Works Order into batches of those not exceeding and those exceeding the amount stated in the Appendix to the Form of Tender.

(6)	When Works Orders, or Complaint Chits, are to be batched and sample checked, random samples of not less than ten per cent (10%) by number and by value of the claimed total value of a batch will be selected for checking.  After checking the dimension book(s) submitted for the sample Works Orders and agreeing any corrections with the Contractor the percentage error between the claimed total values of the samples and the corrected total values of the samples in a batch will be applied to the claimed values of all of the Works Orders in the batch.

(7)	A summary of the batch will be forwarded to the Contractor for his agreement showing the claimed and the checked value of each sample and corrected value of each Works Order supported by corrected dimension book(s) where necessary.

(8)	The Contractor's agreement with the corrected dimension book(s) and the amounts shown on the summary of the batch shall be signified on the summary which shall then be returned to the Maintenance surveyor who shall then certify as correct the value of the Works Orders in the batch and pass such certificate for payment less and interim payments previously made.

(9) Any disagreement with the amount shown on the summary of the batch shall be notified by the Contractor in writing to the Maintenance Surveyor within a period of 90 days from the date on which the summary and corrected dimension book(s), where applicable, were forwarded by the Maintenance Surveyor. If such notice is given all monies which may be due and owing on all of the Works Orders in the batch shall be withheld until agreement or determination of the dispute. If the Contractor fails to sign and return the summary and corrected dimension book(s) and fails to give the notice as aforesaid within the said period of 90 days, the Maintenance Surveyor shall certify as correct the amounts shown on the summary and pass such Certificate for payment, where upon the Contractor shall have no further claims in respect of the Works Orders in the batch.

Interim* payments

80A.	(1)	Interim payments may be made during the progress of the works under any Works Order of an estimated value exceeding that specified in the Appendix to Form of Tender.  Such interim payments shall not exceed eighty per cent (80%) of the estimated value of permanent work executed and materials and goods delivered upon the Site for use in the permanent works which, to the satisfaction of the Maintenance Surveyor are reasonably, properly and not prematurely brought upon the Site and are adequately stored or otherwise protected from damage by weather or other causes.

(2)	No interim payments shall be made on any Works Order of an estimated value not exceeding the amount specified in (1) above.

(3)	One interim payment may be made on completion of the works under any Works Order of an estimated value exceeding that amount specified in the Appendix to the From of Tender.  Such interim payment shall not exceed eighty per cent (80%) of the estimated valued of the work executed or materials or goods supplied.

Provided always that nothing in this clause shall prevent the Maintenance Surveyor if he so requires from making an interim payment of any amount at any time on a Works Order of any estimated value.

Interim* payments

80B.	(1)	Interim payments shall be made in accordance with the schedule set out in the Appendix to the  Form of Tender.

(2)	Notwithstanding the provision of sub-clause (1) hereof, the Maintenance Surveyor shall be at liberty to certify an interim payment of any amount at any time on any Works Order.

(3) On substantial completion of each Works Order as certified by the Maintenance Surveyor he shall also specify work still to be completed under the Works Order, which works must be completed within 90 days of the Maintenance Surveyor’s certificate of substantial completion. If a certificate of substantial completion has been issued the dimension book(s) must be submitted within 90 days of the date of the Maintenance Surveyor’s certificate of substantial completion.

# (Note: 	there are two G. C. C. 79 and one must be deleted)

* (Note:		There are two G. C. C. 80 and one must be deleted.  Clause 80A is applicable if 79A is used and 80B is applicable if Clause 79B is used.  Therefore strike out A or B as the case may require)

(4)	In the event of failure to submit the dimension book(s) for full and final measurement of the work in accordance with Clause 79B the Contractor shall repay immediately either by way of direct payment to the Employer or by way of deduction from any monies due to him from the Employer under this or any other contract the amount paid as interim payments on the Works Order as set out in the Appendix to the Form of  Tender.

| (5) Notwithstanding the provision of sub-clauses (3) and (4) hereof, the Maintenance Surveyor shall be at liberty to extend the stated period within which the dimension book(s) for full and final measurements must be submitted and may waive implementation of sub-clause (4) hereof during the first four months of this Contract. |
| --- |
| Submission of statement of claims for interim payments | 81. The Contractor shall submit to the Maintenance Surveyor a signed statement of any claim for interim payments under Clause 80A or 80B as applicable. Such statements shall be prepared on forms supplied by and at the cost of the Contractor and set out in a manner which shall be determined by the Maintenance Surveyor. After checking and any necessary correction of such statements the Maintenance Surveyor shall prepare certificates for interim payments for such amounts as may be justified by the statements, and pass these certificates to the Employer for payment to the Contractor. |
| Payment on certification | 82. Payment upon each of the Maintenance Surveyor’s certificates shall be made by the Employer within 21 days after the date of the final signature thereon and in the event of failure by the Employer to comply with the provisions of this clause the Employer shall pay to the Contractor interest at the judgment debt rate prescribed from time to time by the Rules of the Supreme Court (Chapter 4 of the Laws of Hong Kong) upon any over-due payment from the date on which the same should have been made. The Employer shall have the power to deduct from any payment due to the Contractor any sum due to the Employer from the Contractor in respect of overpayment on any previous certificate or certified bill or of any other cause whatsoever. Alternatively the Employer may issue a Demand Note to the Contractor for re-payment by the Contractor of any previous over-payment by the Employer, or payment by the Contractor to the Employer in respect of any other matter whatsoever, and the Contractor shall make such repayment or payment to the Employer within 28 days of the issue of the Demand Note. |
| Correction and withholding of certificates | 83. The Maintenance Surveyor may by any certificate make any correction or modification in any previous certificate which shall have been issued by him and shall have power to withhold any certificate of the Works or any part thereof which is not being carried out to his satisfaction. |
| Interim payment certificate or certified bill not to constitute approval of work | 84. No interim payment certificate or certificate or certified bill shall be deemed to constitute approval of any work or other matter in respect of which it is issued or shall be taken as an admission of the due performance of any Works Order or part thereof under the Contract or shall protect or be deemed to protect the Contractor in the case of any over-measurement or over payment or shall constitute a waiver of any rights of the Maintenance Surveyor arising under the Contract against the Contractor or his sureties. |
| Approval of works | 85. The work executed and goods and materials supplied by the Contractor in pursuance of any Works Order under the Contract shall be deemed to be approved by the Maintenance Surveyor unless the Maintenance Surveyor shall disapprove of same in writing within 28 days after the expiry of the Maintenance Period on such Works Order. |
| Maintenance Certificate |

86.	(1)	Upon the expiry of the Maintenance Period in respect of the final Works Order and when all outstanding work referred to under Clause 56 and all work of repair, reconstruction, rectification and making good any defect, imperfection, shrinkage and other fault referred to in Clause 59 shall have been completed the Maintenance Surveyor shall issue a maintenance certificate stating the date on which the Contractor shall have completed his obligation to execute the Works.

(2)	No certificate, other than the maintenance certificate, shall be deemed to constitute approval of any work or other matter in respect of which it is issued or shall be taken as an admission of the due performance of the Contract or any part thereof.

Provided that the maintenance certificate shall not be deemed to constitute approval of any work or other matter in respect of which it is issued which has not been carried out in accordance with the Contract and which the Maintenance Surveyor could not with reasonable diligence have discovered before the issue of the maintenance certificate.

(3)	The issue of any certificate including the maintenance certificate shall not be taken as relieving either the Contractor or the Employer from any liability the one towards the other arising out of or in any way connected with the performance of their respective obligations under the Contract.

| Provided that the Employer shall not be liable to the Contractor for any matter or thing arising out of or in connection with the Contract or the execution of the Works unless the Contractor shall have made a claim in relation thereto in accordance with the time specified in Clause 53 or Clause 67. |
| --- |
|  | REMEDIES AND POWERS |
| Forfeiture |

87.	(1)	If the Contractor shall  become bankrupt or have receiving order made against him or shall present his petition in bankruptcy or shall make an arrangement with or assignment in favour of his creditors or shall agree to carry out the Contract under a committee of inspection of his creditors or (being a corporation) shall go into liquidation (other than a voluntary liquidation for the purposes of amalgamation or reconstruction) or if the Contractor shall assign the Contract without the consent in writing of the Employer being first obtained or shall have an execution levied on his goods or if the Maintenance Surveyor shall certify in writing to the Employer that in his opinion the Contractor:-

(a)	has abandoned the Contract, or

(b)	without reasonable excuse has failed to commence the works in accordance with Clause 49, or

(c)	has suspended the progress of the Works for 14 days after receiving from the Maintenance Surveyor notice in writing to proceed, or

(d)	has failed to comply with an order from the Maintenance Surveyor given in accordance with Clause 48, or

(e)	despite previous warning by the Maintenance Surveyor in writing is failing to proceed with the Works with due diligence or is persistently in breach of any of his obligations under the Contract, or

(f)	has sub-let the whole of the Works; or

(g)	has to the detriment of good workmanship or in defiance of the Maintenance Surveyor’s instruction to the contrary sub-let any part of the Works,

then the Employer may after giving at least 7 days notice in writing to the Contractor enter upon the Site and the Works and expel the Contractor therefrom without thereby avoiding the Contract or releasing the Contractor from any of his obligations or liabilities under the Contract or affecting the rights and powers conferred on the Employer or the Maintenance Surveyor by the Contract and the Employer may complete the Works or may employ any other contractor to complete the Works and the Employer or such other contractor may use for such completion so much of the Constructional Plant, temporary buildings and materials which become the property of the Employer under Clauses 72 and 73 as the Employer may think proper and may at any time sell any of the said Constructional Plant, temporary buildings and unused materials and apply the proceeds of sale in or towards the satisfaction of any sum due or which may become due to the Employer from the Contractor under the Contract.

(2)	As soon as may be practicable after such entry and expulsion by the Employer, the Maintenance Surveyor shall:-

(a)	ascertain and record the quantity of work completed up to such time, and

(b)	ascertain and record the quantities of unused or partially used materials and list any Constructional Plant and temporary buildings which have become the property of the Employer under the Contract.

The provisions of Clause 62 shall apply for the purposes of attendance by the Contractor for measurement and agreement of records and drawings.

(3)	By the notice referred to in sub-clause (1) of this Clause or by further notice in writing within 28 days of the date thereof the Employer may require the Contractor to assign to the Employer and if so required the Contractor shall forthwith assign to the Employer the benefit of any agreement for the supply of any materials and/or for the execution of any work for the purposes of this Contract which the contractor may have entered into.

(4)	If the employer shall expel the Contractor in accordance with this Clause, the Employer shall not be liable to pay the Contractor any money on account of the Contract until:-

(a)	the completion of all those works which are carried out by the Employer’s workmen, and

(b)	the expiry of all maintenance periods, defined by other contracts, of all those works which are carried out by other contractors under such contracts and thereafter until the cost of completion of all Works in respect of  Works Orders issued to the Contractor prior to re-entry, the cost of any work carried out pursuant to Clause 59 which in the opinion of the Maintenance Surveyor would have been required to be carried out at the Contractor’s expense in respect of those Works completed by the Contractor prior to re-entry, damages for delay in completion, if any, and all other expenses incurred by the Employer have been ascertained and the amount thereof certified by the Maintenance Surveyor.

| (5) The Contractor shall then be entitled to receive only such sum, if any, as the Maintenance Surveyor may certify would have been due to the Contractor upon due completion by him of all Works in those Works Orders which had been issued prior to re-entry less the amount certified for the purpose of sub-clause (4) of this Clause. If the amount certified in accordance with sub-clause (4) of this Clause shall exceed the sum which would have been payable to the Contractor on due completion by him of all Works in those Works Orders which had been issued prior to re-entry then the Contractor shall upon demand pay to the Employer the amount of such excess. |
| --- |
| Work by person other than the Contractor | 88. (1) If the Contractor shall fail to carry out any work required under the Contract or refuse to comply with any instruction or order given by the Maintenance Surveyor in accordance with the Contract within a reasonable time, the Maintenance Surveyor may give the Contractor 14 days notice in writing to carry out such work or comply with such instruction. If the Contractor fails to comply with such notice, the Employer shall be entitled to carry out such work or instruction by his own workmen or by other contractors. Without prejudice to any other remedy, all additional expenditure properly incurred by the Employer in having such work or instruction carried out shall be recoverable by the Employer from the Contractor. |
|  | (2) If by reason of any accident or failure or other event occurring to, in or in connection with the Works any remedial or other work shall in the opinion of the Maintenance Surveyor be urgently necessary and the Contractor is unable or unwilling at once to do such remedial or other work, the Maintenance Surveyor may authorize the carrying out of such remedial or other work by a person other than the Contractor. If the remedial or other work so authorized by the Maintenance Surveyor is work which in the Maintenance Surveyor’s opinion the Contractor was liable to do under the Contract, all expenses properly incurred in carrying out the same shall be recoverable by the Employer from the Contractor. Provided that the Maintenance Surveyor shall as soon after the occurrence of any such emergency as may be reasonably practicable notify the Contractor thereof in writing. |
| Recovery of money due to the Employer |

89.	(1)	All damages (including liquidated damages), costs, charges, expenses, debts or sums for which the Contractor is liable to the Employer under any provision of the Contract may be deducted by the Employer from monies due to the Contractor under the Contract and the Employer shall have the power to recover any balance not so deducted from monies due to the Contractor under any other contract between the Employer and the Contractor.

(2)	All damages (including liquidated damages), costs, charges, expenses, debts or sums for which the Contractor is liable to the Employer under any provision of any other contract between the Contractor and the Employer may be deducted by the Employer from monies due to the Contractor under the Contract.

|  | SPECIAL RISKS AND FRUSTRATION |
| --- | --- |
| Special risks |

90.	(1)	If during the currency of the Contract, there shall be :(

(a)	an outbreak of war (whether war be declared or not) in any part of the world which, whether financially or otherwise materially affects the execution of the Works, or

(b)	an invasion of Hong Kong, or

(c)	civil war, rebellion, revolution or military or usurped power in Hong Kong, or

(d)	riot, commotion or disorder in Hong Kong otherwise than amongst the employees of the Contractor, any sub-contractor or Specialist Contractor currently or formerly engaged on the Works or Specialist Works;

hereinafter comprehensively referred to as “the special risks”, the Contractor shall, unless and until the Contract is terminated under the provisions of this Clause, use his best endeavours to complete the execution of the Works.

Provided that the Employer shall be entitled at any time after the occurrence of any of the special risks to terminate the Contract (with the exception of this Clause and Clause 92) by giving written notice to the Contractor, and upon such notice being given the Contract shall terminate but without prejudice to the claims of either party in respect of any antecedent breach thereof.

(2)	In the event of termination in accordance with the proviso to sub-clause (1) of this Clause, the Contractor shall with all reasonable despatch remove from the Site all Constructional Plant and shall similarly allow his sub-contractors to do so.

(3)	In the event of termination in accordance with the proviso to sub-clause (1) of this Clause, the Contractor shall be paid by the Employer, in so far as such items have not already been covered by payments on account made to the Contractor, for all work executed prior to the date of termination at the rates provided in the Contract and in addition : -

(a)	the sums payable in respect of preliminary items in so far as the work or service comprised therein has been carried out or performed and a proper proportion as certified by the Maintenance Surveyor of all such items the work or service comprised in which has been partially carried out or performed;

(b)	the cost of materials reasonably ordered for the works which shall have been delivered to the Contractor or of which the Contractor is legally liable to accept delivery, such materials becoming the property of the Employer upon such payment being made by the Employer;

(c) a sum to be certified by the Maintenance Surveyor being any Cost reasonably incurred by the Contractor in the expectation of completing the whole of the Works in so far as such Cost shall not have been paid in accordance with any other sub-clause of this Clause;

(4)	Whether the Contract shall be determined in accordance with the proviso to sub-clause (1) of this Clause or not, the following provisions shall apply or be deemed to have applied as from the occurrence of any of the special risks notwithstanding anything expressed in or implied by the other terms of the Contract : (

(a)	The Contractor shall be under no liability whatsoever whether by way of indemnity or otherwise for or in respect of damage to the permanent work (other than work condemned under Clause 48) or Temporary Works or to property other than property of the Contractor including property deemed to be the property of the Employer under Clause 72 or property hired by the Contractor for the purposes of executing the Works) whether of the Employer or of third parties or for or in respect of injury or loss of life which is wholly the consequence of the occurrence of any of the special risks and the Employer shall indemnify the Contractor against all such liabilities and against all claims, demands, proceedings, damages, costs, charges and expenses whatsoever in respect of or in relation thereto.

(b)	If the permanent work or Temporary Works or any material on the Site shall be destroyed or damaged by reason of any of the special risks, the Contractor shall nevertheless be entitled to payment for any permanent work and for any materials so destroyed or damaged and the Contractor shall be entitled to recover from the Employer the expense incurred in making good any such destruction or damage whether to the permanent work or the Temporary Works and of replacing or making good such materials so far as may be required by the Maintenance Surveyor or as may be necessary for the completion of  the Works, valued at rates agreed upon between the Maintenance Surveyor and the Contractor and based where possible on prime costs.  In the event of the Maintenance Surveyor and Contractor failing to reach agreement on any rate the Maintenance Surveyor shall fix such rate as shall in his opinion be reasonable and notify the Contractor accordingly.

(c) Destruction, damage, injury or loss of life caused by the explosion or impact, whenever and wherever occurring, of any mine, bomb, shell, grenade, missile, munition or explosive of war shall be deemed to be a consequence of the special risks.

Frustration

91.	In the event of the Contract being frustrated whether by war or otherwise howsoever, the sum payable by the Employer to the Contractor shall be the same as that which would have been payable under Clause 90 if the Contract had been terminated in accordance with Clause 90.

|  | SETTLEMENT OF DISPUTES |
| --- | --- |

Settlement of

disputes

92.	(1)	If any dispute or difference of any kind whatsoever shall arise between the Employer and the Contractor in connection with or arising out of the Contract or the carrying out of the Works including any dispute as to any decision, instruction, order, direction, certificate or valuation by the Maintenance Surveyor whether during the progress of the Works or after their completion and whether before or after the termination, abandonment or breach of the Contract, it shall be referred to and settled by the Maintenance Surveyor who shall state his decision in writing and give notice of the same to the Employer and the Contractor.  Unless the Contract shall have been already terminated or abandoned the Contractor shall in every case continue to proceed with the Works with all due diligence and he shall give effect forthwith to every such decision of the Maintenance Surveyor unless and until the same shall be revised by an arbitrator as hereinafter provided.  Such decisions shall be final and binding upon the Contractor and the Employer unless either of them shall require that the matter be referred to arbitration as hereinafter provided.  If the Maintenance Surveyor shall fail to give such decision for a period of 90 days after being requested to do or if either the Employer or the Contractor be dissatisfied with any such decision of the Maintenance Surveyor then either the Employer or the Contractor may within 90 days after receiving notice of such decision, or within 90 days after the expiration of the said decision period of 90 days, as the case may be, require that the matter shall be referred to arbitration in accordance with and subject to the provisions of the Arbitration Ordinance or any statutory modification thereof for the time being in force and any such reference shall be deemed to be a submission to arbitration within the meaning of such Ordinance.  The arbitrator appointed shall have full power to open up review and revise any decision (other than a decision under Clause 48(3) not to vary the Works), instruction, order, direction, certificate or valuation by the Maintenance Surveyor and neither party shall be limited in the proceedings before such arbitrator to the evidence or arguments put before the Maintenance Surveyor for the purpose of obtaining his decision above referred to.  Save as provided for in sub-clause (2) of this Clause no steps shall be taken in the reference to the arbitrator until after the completion or alleged completion of the whole of the Works unless with the written consent of the Employer and the Contractor.  Provided that :(

(a)	the giving of a Certificate of Completion under the Contract in respect of the final Works Order shall not be a condition precedent to the taking of any step in such reference;

(b)	no decision given by the Maintenance Surveyor in accordance with the foregoing provisions shall disqualify him from being called as a witness and giving evidence before the arbitrator on any matter whatsoever relevant to the dispute or difference referred to the arbitrator as aforesaid.

(2)	In the case of any dispute or difference as to the exercise of the Maintenance Surveyor’s powers  under Clause 87(1) the reference to the arbitrator may proceed notwithstanding that the Works shall not then be or be alleged to be complete.

(3)	The Lands and Works Model Arbitration Rules shall apply to any arbitration instituted in accordance with this Clause unless the parties agree to the contrary.

|  | NOTICES |
| --- | --- |

Service of

notices

93.	(1)	Any notice to be given to the Contractor under the provisions of the Contract must be in writing and may be served : -

(a)	personally, or

(b)	by post addressed to the Contractor’s last known place of business or, in the event of the Contractor being

(i)	a firm, to the last known place of residence of the owner or any of the partners thereof, or

(ii)	a company, at the registered office in Hong Kong of such company, or

(c)	by leaving a copy at the Contractor’s last known place of business or, in the event of the Contractor being

(i)	a firm, to the last known place of residence of the owner or any of the partners thereof, or

(ii)	a company, at the registered office in Hong Kong of such company, or

(d)	by posting a copy in a conspicuous position upon the Site.

(2)	Any notice to be given to the Maintenance Surveyor under the provisions of the Contract shall be served by sending the same by post to or leaving the same at the office of the Maintenance Surveyor.

(3)	Any notice to be given to the Employer, as distinct from the Maintenance Surveyor, under the provisions of the Contract shall be served by sending the same by post or leaving the same at the appropriate management office of the Employer.

DEFAULT OF THE EMPLOYER

Default of the Employer

94.	(1)	In the event of the Employer failing to pay to the Contractor any sum certified in accordance with Clause 79 and 81 within 30 days after the same shall have become due under the provisions of the Contract the Contractor may give 14 days notice in writing to the Employer to make payment of the sum due.  Such notice shall make express reference to this Clause.  In the event of failure by the Employer to make such payment within such 14 day notice period, the Contractor shall be entitled to terminate the Contract.

(2)	In the event of the Contract being terminated under this Clause the property in all Constructional Plant and temporary buildings brought upon the Site by the Contractor shall thereupon revest in him and he shall with all reasonable despatch remove the same from the Site.

(3) Nothing in this Clause contained shall prejudice the right of the Contractor to exercise, either in lieu of or in addition to the rights and remedies in this Clause specified, any other rights or remedies to which the Contractor may be entitled.