| Clause | Remarks/Guidelines |
| --- | --- |
| NTT B2 Constraints on Service Manager’s power |  |
| - The tenderer’s attention is drawn to the constraints on the Service Manager’s powers set out in ACC Clause [III:1]#. | Please refer to WBTC Nos. 19/2000, 20/2000 and 16/2002, ETWB TCW Nos. 56/2002A and 6/2004, and DEVB TCW No. 5/2007 |
| (2) In addition to the above constraints, the Service Manager is also required under the terms of its appointment by the Client to: |  |
| (i) refer the details of every change to the Scope, including the reasons for the change, its estimated change to the Prices due to the associated compensation event or creation of a new item in the Price List, to the Client for information as soon as the change is ordered; | # Insert as appropriate |
| (ii) refer the details of the evaluation to the Client for information as soon as the change to the Prices due to the compensation event associated with the change to the Scope or creation of a new item in the Price List has been determined; |  |
| (iii) report to the Client all compensation events involving changes to the Prices or all creation of new items in the Price List and refer to the principles underlying its assessment of each compensation event or each new item in the Price List to enable the Client to provide its view of the matter before the Service Manager reaches a decision; and |  |
| (iv) report to the Client all compensation events involving delays to the Task Completion Dates, except for those delays solely in respect of inclement weather conditions, refer to the principles underlying its assessment of each compensation event to enable the Client to provide its view of the matter before the Service Manager reaches a decision. | Add any other constraints as necessary and specified in the consultancy agreements other than the above. |